Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  September 25, 2019


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   +12 C; raining
	Persons on site: Don Cook, Mike ?


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	R/W Felling
	
	 Excavator, 



ACTIVE EQUIPMENT
- hoe pilot and pushover falling
- hoe sorting and hand bucking pushover

R/W
- pilot trail to approximately Hub 45.
- pushover falling within the R/W complete to Hub 45.
- pushover trees piled along lower R/W.
- no landings constructed to date.

GRUBBING and STRIPPING
- Partial stripping has been completed for approximately 100 m;  timber decks are impeding additional area.

DEBRIS DISPOSAL
- none to date

SUBGRADE
- none to date

DRAINAGE
- no culverts installed to date
- temp xing installed at Hub 30, 1200 mm culvert location; draining well; no issues

ENDHAUL
- None to date

DRILL and BLASTING
- none to date
- the larger boulders may require blasting if too big to move.


DISCUSSIONS
EMS and Safety
- Discussed current site congestion due to push over of all r/w width prior to construction of landings or pilot trail.  Suggested that future debris disposal, material movement and drainage could become compromised with this method.
- Emphasized that operations cannot spill over-onto public road
[bookmark: _GoBack]- As per request, D8 and water tank will be moved up 8500 today, off of the public road.
- Discussed drainage; hoe to x- ditch the pilot trail at low points for the weekend
-Signage in place; safe practises being implemented
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