Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: September 25, 2019 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: +12 C; raining |  | Persons on site: Don Cook, Mike ? |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | R/W Felling |  | Excavator, |

ACTIVE EQUIPMENT

- hoe pilot and pushover falling

- hoe sorting and hand bucking pushover

R/W

- pilot trail to approximately Hub 45.

- pushover falling within the R/W complete to Hub 45.

- pushover trees piled along lower R/W.

- no landings constructed to date.

GRUBBING and STRIPPING

- Partial stripping has been completed for approximately 100 m;  timber decks are impeding additional area.

DEBRIS DISPOSAL

- none to date

SUBGRADE

- none to date

DRAINAGE

- no culverts installed to date

- temp xing installed at Hub 30, 1200 mm culvert location; draining well; no issues

ENDHAUL

- None to date

DRILL and BLASTING

- none to date

- the larger boulders may require blasting if too big to move.

DISCUSSIONS
EMS and Safety

- Discussed current site congestion due to push over of all r/w width prior to construction of landings or pilot trail.  Suggested that future debris disposal, material movement and drainage could become compromised with this method.

- Emphasized that operations cannot spill over-onto public road

- As per request, D8 and water tank will be moved up 8500 today, off of the public road.

- Discussed drainage; hoe to x- ditch the pilot trail at low points for the weekend
-Signage in place; safe practises being implemented

Photos