EN21TFD008– Kokanee 8100 and 6500
Final Spur Inspection
	Inspector:  Gary Shannon
	Date:  June 7, 2021


	Contract #: EN21TFD008 - Recommence
	Contractor Name: Alpine Logging Ltd.


	Weather:   10 C; overcast
	Persons on site:  NONE


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	No active operations
	Kokanee 8500
	 NONE

	8510
	No active operations
	8510
	N/A




SPUR 6500

R/W
- 100 % complete per requirements
- all wood removed and previous landings tidy

GRUBBING and STRIPPING
- 100% complete per requirements

DEBRIS DISPOSAL
- debris has been piled for fall burning.

ENDHAUL
The following are payment items finalized with Alpine:
- 28 loads at 10 m3 / haul up from junction and utilized on road grade.
- 2 loads hauled up to Hub 30 on 8500 Spur for culvert bedding.
- 1 load of crush hauled and spread at junction $ 590.00.

DRILL and BLASTING
- none required 

SUBGRADE
- 100% complete to POT, per contract requirements

DRAINAGE
- 4, 450 mm culverts installed on spur. 36 m
- 2, 600 mm culverts installed on spur. 18 m
- 1, 450 mm culvert installed at junction across MOT road. 9 m
- 1, 600 mm culvert installed across MOT road down slope from Hub 47 on spur. 9 m

SPUR 8100

R/W
- 100% complete.
- all wood removed.

GRUBBING and STRIPPING
- 100% complete

DEBRIS DISPOSAL
- debris has been piled for fall burning.

ENDHAUL
Additional Payment Item:
- 1 load of crush hauled and spread at junction, $ 590.00

DRILL and BLASTING
- none required

SUBGRADE
- 100% complete

DRAINAGE
- 3, 450 mm culverts installed on spur. 27 m
- 1, 450 mm culvert installed at junction across MOT road. 9 m

OTHER
- light seasonal deac installed on both spurs.
- grass seeding complete on both spurs.
- neat and tidy construction.
- deac signs posted on both spurs.
-Requires SPUR NAME SIGNS
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