EN21TFD008– Kokanee 8100 and 6500

Final Spur Inspection

| Inspector: Gary Shannon |  | Date: June 7, 2021 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD008 - Recommence |  | Contractor Name: Alpine Logging Ltd. |  |
| Weather: 10 C; overcast |  | Persons on site: NONE |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | No active operations | Kokanee 8500 | NONE |
| 8510 | No active operations | 8510 | N/A |

SPUR 6500

R/W

- 100 % complete per requirements

- all wood removed and previous landings tidy

GRUBBING and STRIPPING

- 100% complete per requirements

DEBRIS DISPOSAL

- debris has been piled for fall burning.

ENDHAUL

The following are payment items finalized with Alpine:

- 28 loads at 10 m3 / haul up from junction and utilized on road grade.

- 2 loads hauled up to Hub 30 on 8500 Spur for culvert bedding.

- 1 load of crush hauled and spread at junction $ 590.00.

DRILL and BLASTING

- none required

SUBGRADE

- 100% complete to POT, per contract requirements

DRAINAGE

- 4, 450 mm culverts installed on spur. 36 m

- 2, 600 mm culverts installed on spur. 18 m

- 1, 450 mm culvert installed at junction across MOT road. 9 m

- 1, 600 mm culvert installed across MOT road down slope from Hub 47 on spur. 9 m

SPUR 8100

R/W

- 100% complete.

- all wood removed.

GRUBBING and STRIPPING

- 100% complete

DEBRIS DISPOSAL

- debris has been piled for fall burning.

ENDHAUL

Additional Payment Item:

- 1 load of crush hauled and spread at junction, $ 590.00

DRILL and BLASTING

- none required

SUBGRADE

- 100% complete

DRAINAGE

- 3, 450 mm culverts installed on spur. 27 m

- 1, 450 mm culvert installed at junction across MOT road. 9 m

OTHER

- light seasonal deac installed on both spurs.

- grass seeding complete on both spurs.

- neat and tidy construction.

- deac signs posted on both spurs.

-Requires SPUR NAME SIGNS

PHOTOS