## Sheet2
BCTS 2021 Archaeology Work plan- BCTS TOC
Block | TSL | Area | BCTS Zone (SZ, NZ, CZ) | Referral Year | Consultant (Ursus, Splats, ALIB) | Leading FN | Comments | Report Due Date | Assessment type (PFR, AIA) | Maps Uploaded | Report received | OG
K5R2 | TA1223 | Hope/Goodfellow | CZ | 2021 |  | NIB or ALIB? |  |  | PFR | Yes | 2021-11-04
K5YZ | TA1344 | Barton | SZ | 2021 |  | OKIB |  |  | PFR | Yes | 2021-11-04
K68T | TA1787 | Barton | SZ | 2021 |  | OKIB |  |  | PFR | Yes | 2021-11-04
K6MS | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K6QY | TA1341 | Banting | SZ | 2021 |  | Splatsin |  | 2 | PFR |  | 2021-10-15
K735 | TA1223 | Hope/Goodfellow | CZ | 2021 |  | NIB or ALIB? |  |  | PFR | Yes | 2021-11-04
K7G8 | TA1216 | Cascadia | CZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-27
K7K5 | TA1341 | Banting | SZ | 2021 |  | Splatsin |  | 2 | PFR |  | 2021-10-15
K7QP | TA1223 | Hope/Goodfellow | CZ | 2021 |  | NIB or ALIB? |  |  | PFR | Yes | 2021-11-04
K7S9 | TA1177 | Swan | CZ | 2021 |  | ALIB |  |  | PFR | Yes | 2021-09-01
K82W | !Planning South | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K881 | TA1784 | Adelphi | SZ | 2021 |  | Splatsin |  | 3 | PFR |  |  | Recruitment
K88Q | TA1409 | Mission (SZ) | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-21
K8B7 | TA1342 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-08-26
K8B9 | TA1342 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-08-26
K8BB | TA1342 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-08-26
K8BP | TA1790 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8BU | TA1791 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8BW | TA1791 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8BY | TA1791 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8C2 | TA1791 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8C4 | TA1792 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8CG | TA1343 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-10-15
K8D5 |  | Bolean | SZ | 2021 |  | Splatsin |  |  | PFR |  |  | Recruitment Polygon
K8DR | TA1268 | Skaha | SZ | 2021 |  | PIB |  |  | PFR | Yes | 2021-08-26
K8NG | TA1340 | Graystokes | SZ | 2021 |  | WFN |  |  | PFR | Yes | 2021-11-04
K8NL | TA1340 | Graystokes | SZ | 2021 |  | WFN, PIB |  |  | PFR | Yes
K8NQ | TA1340 | Graystokes | SZ | 2021 |  | WFN, PIB |  |  | PFR | Yes |  | Majority within OG
K8QQ | TA1786 | Banting | SZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-15
K8QS | TA1785 | Banting | SZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-15
K8QY | TA1785 | Banting | SZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-15
K8R2 | TA1785 | Banting | SZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-15
K8RF |  | Bolean | SZ | 2021 |  | Splatsin |  |  | PFR
K8S8 | 1339 | Paxton | SZ | 2021 |  | Splatsin |  | 2 | PFR
K8SY | 1339 | Paxton | SZ | 2021 |  | Splatsin |  | 2 | PFR
K8TA | TA1345 | Mellin Windy | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-20
K8TC | TA1345 | Mellin Windy | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-13
K8TE | TA1345 | Mellin Windy | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-13
K8TG | TA1345 | Mellin Windy | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-13
K8TL | TA1679 | Mellin Windy | SZ | 2021 |  | OKIB, WFN |  |  | PFR | Yes | 2021-09-13
K8W5 | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K8W8 | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K8WF | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K8WL | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K8Y4 | TA1192 | Ice River | CZ | 2021 |  | SIB? |  |  | PFR | Yes | 2021-10-12
K8ZC | A45874 | Mt. Seven | CZ | 2021 |  | NIB |  |  | PFR | Yes | 2021-09-21
K8ZW | !Planning TFL49 | TFL49 - Okanagan | SZ | 2021 |  | WFN, OKIB |  |  | PFR | Yes | 2021-11-19 | OG
K8ZY | !Planning TFL49 | TFL49 - Okanagan | SZ | 2021 |  | WFN, OKIB |  |  | PFR | Yes | 2021-11-19 | OG
K908 | !Planning TFL49 | TFL49 - Okanagan | SZ | 2021 |  | WFN |  |  | PFR | Yes | 2021-09-20
K90B | !Planning TFL49 | TFL49 - Okanagan | SZ | 2021 |  | WFN |  |  | PFR | Yes | 2021-09-07
K90H | TA0511 | Kal Slopes | NZ | 2021 |  | Splatsin |  | 1 | PFR |  | 2021-10-12
K95J |  | Kal Slopes | NZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-12
K95L |  | Kal Slopes | NZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-11-04
K95R |  | Kal Slopes | NZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-11-04
K95W |  | Kal Slopes | NZ | 2021 |  | Splatsin |  | 3 | PFR |  | 2021-10-15
K0X3 | A94421 | Currie | NZ | 2020 | Ursus | NIB | Referred in 2019, selected by Ursus for PFR | 2021-09-01 | PFR | Y | 2021-06-17
K1YZ | TA0494 | Currie | NZ | 2020 | Ursus | OKIB | 22- Q2 sale - OKIB identified three potential AOPs in 2019 | 2021-06-01 | PFR | Y | 2021-06-17
K58E | TA1136 | Mugford | NZ | 2020 | Ursus | Westbank |  | 2021-11-01 | PFR | Y | 2021-11-04
K5C8 | TA0494 | Currie | NZ | 2020 | Ursus | OKIB | 22-Q2 sale - OKIB identified a possible Cairn in 2019 | 2021-06-01 | PFR | Y | 2021-06-17
K62E | TA1159 | Barton | SZ | 2020 | Ursus | OKIB, | PFR request by OKIB | 2021-09-01 | PFR | Y | 2021-07-19
K62H | TA1159 | Barton | SZ | 2020 | Ursus | OKIB, UNIB |  | 2021-09-01 | PFR | Y | 2021-07-19
K69E | TA1159 | Barton | SZ | 2020 | Ursus | OKIB, UNIB |  | 2021-09-01 | PFR | Y | 2021-07-19
K6N8 |  | Mara | NZ | 2020 | Urusu | Splatsin, OKIB |  |  |  |  | 2021-05-05
K6SN |  | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-05-01 | PFR | Y | 2021-05-21
K74K | TA0924 | Mission | SZ | 2020 | Ursus | OKIB, WFN |  | 2021-06-01 | PFR | Y | 2021-09-20
K76D | TA0893 | Graystokes | SZ | 2020 | Ursus | OKIB, WFN | Was supposed to be dropped, Ursus assesed anyway | 2021-05-01 | PFR | Y | 2021-08-05
K780 | TA0923 | Mission | SZ | 2020 | Ursus | OKIB |  | 2021-11-01 | PFR | Y | 2021-08-05
K781 | TA0923 | Mission | SZ | 2020 | Ursus | OKIB |  | 2021-11-01 | PFR | y | 2021-08-05
K782 | TA0923 | Mission | SZ | 2020 | Ursus | OKIB |  | 2021-11-01 | PFR | Y | 2021-09-21
K7G3 | TA1172 | Cascadia | CZ | 2020 | Ursus | none (all FNs completed reviews in 2020, except OKIB) | 22-Q2 sale | 2021-05-01 | PFR | Y | 2021-06-03
K7HV | TA0921 | Skaha | SZ | 2020 | Ursus | PIB | Interin Draft report received | 2021-04-30 | AIA | Y | 2021-06-24
K7K2 | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K7MX | A70816 | Paxton | SZ | 2020 | Splatsin | Splatsin, OKIB | AIA at AOP's. OKIB missed CHA in 2020. Sp and Okib work together?? Interim Report Received | 2021-06-30 | AIA | Y | 2021-06-22
K7MZ | TA0893 | Graystokes | SZ | 2020 | Ursus | OKIB, WFN |  | 2021-05-01 | PFR | Y | 2021-07-28
K7N0 | TA0895 | Graystokes | SZ | 2020 | Ursus | OKIB | Received OKIB invoice | 2021-05-01 | PFR | Y | 2021-08-11
K7N1 | TA0895 | Graystokes | SZ | 2020 | Ursus | OKIB | Received OKIB invoice | 2021-05-01 | PFR | Y | 2021-08-11
K7N3 | TA0891 | Graystokes | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y |  | Majority in OG
K7N4 | TA0891 | Graystokes | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-11-04
K7N9 | TA0894 | Banting | SZ | 2020 | Ursus/ Splatsin | Splatsin | PFR's done by Sp and Ursus in 2020, needed for Q2, interim draft report received | 2021-04-30 | AIA | Y | 2021-06-22
K7NB | TA0894 | Banting | SZ | 2020 | Ursus | Splatsin |  |  |  | Y | 2021-07-20
K7ND | TA0922 | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-05-01 | PFR | Y | 2021-05-21
K7QY | TA1178 | Esplanade | CZ | 2020 | Ursus | Adams Lake | 22-Q2 sale | 2021-05-01 | PFR | Y | 2021-06-03
K7U2 | TA0508 | Echo | NZ | 2020 | Ursus | OKIB | requested by OKIB, 22-Q2 sale | 2021-05-01 | PFR | Y | 2021-06-03
K7U5 | TA0508 | Echo | NZ | 2020 | Ursus | OKIB | 22-Q2 sale | 2021-05-01 | PFR | Y | 2021-06-03
K82U | TA0922 | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-05-01 | PFR | Y | 2021-05-21
K850 | TA1176 | Swan | CZ | 2020 | Ursus | none (all FNs completed reviews in 2020) | DROPPED - no review required | 2021-09-01 | PFR | N/A | N/A
K852 | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K854 | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K856 | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K85C | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K85E | TA0892 | Big White | SZ | 2020 | Ursus | WFN |  | 2021-09-01 | PFR | Y | 2021-09-21
K85J | TA1179 | Esplanade | CZ | 2020 | Ursus | none (all FNs completed reviews in 2020) |  | 2021-11-01 | PFR | Y | 2021-06-09
K85L | TA1179 | Esplanade | CZ | 2020 | Ursus | none (all FNs completed reviews in 2020) |  | 2021-11-01 | PFR | Y | 2021-06-09
K85P | TA1179 | Esplanade | CZ | 2020 | Ursus | Neskonlith |  | 2021-11-01 | PFR | Y | 2021-11-19
K86T | TA1159 | Barton | SZ | 2020 | Ursus | OKIB, UNIB |  | 2021-09-01 | PFR | Y | 2021-07-19
K87V | TA0406 | Adelphi | SZ | 2020 | Splatsin | Splatsin | AIA at AOP's. OKIB missed CHA in 2020. Sp and Okib work together?? | 2021-06-30 | AIA | Y |  | Burned
K89P | TA1266 | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-09-01 | PFR | Y | 2021-05-21
K89U | TA1266 | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-09-01 | PFR | Y | 2021-05-21
K8E3 | TA1266 | Skaha | SZ | 2020 | Ursus | PIB |  | 2021-09-01 | PFR | Y | 2021-05-21