## 2018
Date of Last Update: |  | 2018-10-17 |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2019-2023
Updated by: |  | Gail Campbell
"Licencee" | TSL | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A64102 | 1 | 40.4 | 19875 | Williams Creek Area | 103I049 | ALL | 2019 | C
BCTS | A78680 | TEsa002 | 51.4 | 12000 | Sandur | 103I0048 | ALL | 2022 | F
BCTS | A79851 | 1 | 20 | 10698 | Skeena West | 103I089 | ALL | 2019 | F
BCTS | A79851 | TEsw022 | 9.2 | 3597 | Skeena West | 103I089 | ALL | 2019 | C
BCTS | A79851 | TEsw030 | 39.2 | 18315 | Skeena West | 103I089 | ALL | 2019 | C
BCTS | A80642 | 2 | 17 | 5867 | Skeena West | 103I079 | ALL | 2021 | C
BCTS | A85649 | TEsw016 | 29.8 | 10006 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A85649 | TEsw046 | 13.7 | 6576 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A85649 | TEsw051 | 11.6 | 5901 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A90583 | 64124-1 | 8.5 | 3603 | Skeena West | 103I089 | ALL | 2023 | F
BCTS | A90583 | TEsw025 | 15.8 | 7631 | Skeena West | 103I089 | ALL | 2023 | F
BCTS | A95103 | TEbc055 | 23.9 | 11070 | Big Cedar | 103P018 | ALL | 2019 | C
BCTS | A95103 | TEbc056 | 17.9 | 4937 | Big Cedar | 103P019 | ALL | 2019 | C
BCTS | A95769 | TEbc044 | 46.9 | 19932.5 | Big Cedar | 103P017 | ALL | 2019 | C
BCTS | A95770 | TEbc059 | 21.6 | 19003 | Big Cedar | 103P007 | ALL | 2020 | F
BCTS | A95770 | TEbc061 | 70 | 42165 | Big Cedar | 103P007 | ALL | 2022 | F
BCTS | A95770 | TEbc080 | 15 | 7270 | Big Cedar | 103P007 | ALL | 2020 | F
BCTS | A95771 | TEth007 | 13.2 | 4639 | Thunderbird | 103I048 | ALL | 2021 | F
BCTS | A95771 | TEth027 | 5.5 | 4899 | Thunderbird | 103I048 | ALL | 2021 | F
BCTS | A95771 | TEth028 | 12 | 3573 | Thunderbird | 103I048 | ALL | 2021 | F
BCTS | Unassigned | TEbc006 | 20 | 8000 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc007 | 18 | 6000 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc017 | 40 | 15000 | Big Cedar | 103P018 | ALL | 2022 | R
BCTS | Unassigned | TEbc057 | 29.9 | 15385 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc058 | 28.4 | 12009 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc060 | 20.4 | 11193 | Big Cedar | 103P019 | ALL | 2022 | R
BCTS | Unassigned | TEbc081 | 42.7 | 15854 | Big Cedar | 103P007 | ALL | 2022 | R
BCTS | Unassigned | TEkz002 | 31 | 22080 | Kleanza | 103I058 | ALL | 2021 | F
BCTS | Unassigned | TEkz003 | 14 | 7085 | Kleanza | 103I058 | ALL | 2021 | F
BCTS | Unassigned | TEsw012 | 25 | 10000 | Skeena West | 103I068 | ALL | 2021 | R
BCTS | Unassigned | TEsw020 | 3 | 1175 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw021 | 23 | 3000 | Skeena West | 103I089 | ALL | 2023 | R
BCTS | Unassigned | TEsw028 | 17 | 6000 | Skeena West | 103I089 | ALL | 2023 | R
BCTS | Unassigned | TEsw032 | 2.3 | 900 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw033 | 29.5 | 11815 | Skeena West | 103I079 | ALL | 2020 | R
BCTS | Unassigned | TEsw038 | 10 | 4050 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw039 | 32 | 7000 | Skeena West | 103I069 | ALL | 2020 | R
BCTS | Unassigned | TEsw040 | 16.2 | 6175 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw041 | 8 | 3150 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw042 | 16 | 6800 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw043 | 16 | 6300 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw044 | 14.4 | 5760 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | Unassigned | TEsw045 | 31 | 16400 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | A90581 | TEsw050 | 32.7 | 13701 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | Unassigned | TEsw052 | 24 | 12524 | Skeena West | 103I079 | ALL | 2023 | R
BCTS | A95864 | TEsw056 | 27.1 | 13819 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A95864 | TEsw057 | 10.6 | 4402 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A95864 | TEsw058 | 33.3 | 16256 | Skeena West | 103I079 | ALL | 2021 | F
483390.5
| Annual Allocation within Kalum TSA: |  | 88228
Annual Allocation x 5 years |  |  | 441140
|  | Total volume identified: | 483390.5
|  | Years of supply: | 5.4789