## Sheet1
Date of Last Update: | November 1st 2013 |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA
Updated by: | Gail Campbell
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A64093--3 | 61.6021 | 27194 | Limonite | 093L051 | unknown | 2014 | F
BCTS | A64094--1 | 28.8 | 10014.2703 | Limonite | 093L051 | unknown | 2014 | F
BCTS | A64094--2 | 30.3 | 12004.1418 | Limonite | 093L051 | unknown | 2014 | F
BCTS | A80876--1 | 45.5 | 22952.9194 | No Gold Area | 093L051 | unknown | 2014 | F
BCTS | A80876--2 | 50.5 | 25475.2168 | No Gold Area | 093L051 | unknown | 2014 | F
BCTS | A85519--1 | 51.7 | 21260.0846 | Kitanayakwa | 093L051 | unknown | 2014 | F
BCTS | !PlanningC--TEki019 | 79.9064 | 38000 | Kitanayakwa | 093L041 | unknown | 2015 | R
BCTS | !PlanningC--TEki020 | 22.3568 | 9350 | Kitanayakwa | 093L041 | unknown | 2015 | R
BCTS | !PlanningC--TEki021 | 34.4589 | 13175 | Kitanayakwa | 093L041 | unknown | 2015 | R
BCTS | !PlanningC--TElm020 | 34.419 | 14450 | Limonite | 93L051 | unknown | 2015 | R
BCTS | !PlanningC--TElm021 | 30.4116 | 13175 | Limonite | 93L051 | unknown | 2015 | R
BCTS | !PlanningC--TElm022 | 14.46 | 5600 | Limonite | 093L051 | unknown | 2015 | R
BCTS | A85651--TElm013 | 31.5 | 13597 | Limonite | 093L051 | unknown | 2015 | F
BCTS | !PlanningC--TEki022 | 32.2888 | 10875 | Kitanayakwa | 093L041/093L051 | unknown | 2016 | R
BCTS | !PlanningC--TEki026 | 10.5238 | 6300 | Kitanayakwa | 093L041 | unknown | 2016 | R
BCTS | !PlanningC--TElm008 | 30.4069 | 13500 | Limonite | 093L051 | unknown | 2016 | R
BCTS | !PlanningC--TElm009 | 46.3705 | 21850 | Limonite | 093L051 | unknown | 2016 | R
BCTS | !PlanningC--TElm010 | 31.9048 | 12900 | Limonite | 093L051 | unknown | 2016 | R
BCTS | !PlanningC--TElm023 | 29.5175 | 11800 | Limonite | 93L051 | unknown | 2016 | R
BCTS | !PlanningC--TElm024 | 45.7421 | 17250 | Limonite | 93L041\93L051 | unknown | 2016 | R
BCTS | !PlanningC--TElm025 | 21.0431 | 8400 | Limonite | 93L041 | unknown | 2016 | R
BCTS | !PlanningC--TElm026 | 25.8822 | 10838 | Limonite | 093L051 | unknown | 2016 | R
BCTS | !PlanningC--TEbc021 | 18.2663 | 6500 | Big Cedar | 103I096 | unknown | 2017 | R
BCTS | !PlanningC--TEbc022 | 16.2326 | 6000 | Big Cedar | 103I096 | unknown | 2017 | R
BCTS | !PlanningC--TEbc035 | 24 | 8250 | Big Cedar | 103I096 | unknown | 2017 | R
BCTS | !PlanningC--TEbc036 | 56.0331 | 25713 | Big Cedar | 103I096/103P006 | unknown | 2017 | R
BCTS | !PlanningC--TElm001 | 53.0094 | 20800 | Limonite | 093L051 | unknown | 2017 | R
BCTS | !PlanningC--TElm003 | 14.6916 | 11900 | Limonite | 093L041/093L051 | unknown | 2017 | R
BCTS | !PlanningC--TEng005 | 39.2512 | 15600 | No Gold Area | 103I060\93L051 | unknown | 2017 | R
BCTS | !PlanningC--TEng006 | 26.2579 | 11050 | No Gold Area | 103I060\93L051 | unknown | 2017 | R
BCTS | !PlanningC--TEki007 | 27 | 12825 | Kitanayakwa | 093L041 | unknown | 2018 | R
BCTS | !PlanningC--TEki018 | 14.6602 | 5250 | Kitanayakwa | 093L041/042/031/032 | unknown | 2018 | R
BCTS | !PlanningC--TElm004 | 28.4728 | 13050 | Limonite | 093L051 | unknown | 2018 | R
BCTS | !PlanningC--TElm011 | 43.6 | 16800 | Limonite | 093L051 | unknown | 2018 | R
BCTS | !PlanningC--TElm015 | 43.4653 | 19350 | Limonite | 093L041 | unknown | 2018 | R
BCTS | A79849 | 54.2 | 35493 | Kitnayakwa | 093L041 | unknown | 2014 | C
BCTS | A86361 | 75.5 | 33525 | Kitnayakwa | 093L041 | unknown | 2014 | C
BCTS | A79850 | 91.1 | 58467 | Kitnayakwa | 093L041 | unknown | 2014 | C
640533.633
| Total volume identified: | 640533.633
| Annual Allocation within Cascadia TSA: | 121941
| Allocation X 5 years: | 609745
| Years of supply: | 5.3
Note on B53: Rick: A&A: 13052 m3 allocation BCTS: 88228 CTR: 244037 KVL: 14454 KFP: 14454