## Sheet1
Date of Last Update: | March 1st 2013 |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA
Updated by: | Gail Campbell
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A81413 | 1.3 | 685 | Thunderbird | 103I067 | unknown | 2013 | C
BCTS | A77838 | 11.3 | 5907 | Skeena West | 103I089 | unknown | 2013 | C
BCTS | A85596 | 76.8 | 57360 | Big Cedar | 103P007 | unknown | 2013 | C
BCTS | A85595-1, 2,3 | 96.5 | 58025 | Big Cedar | 103P007 | unknown | 2013 | C
BCTS | !Planningb--TEbc013 | 46.5 | 18275 | Big Cedar | 103P007 | unknown | 2015 | R
BCTS | !Planningb--TEbc020 | 27.4 | 14985 | Big Cedar | 103P007 | unknown | 2016 | W
BCTS | !Planningb--TEbc025 | 39.9 | 18430 | Big Cedar | 103P007 | unknown | 2015 | R
BCTS | !Planningb--TEbc031 | 33 | 14104 | Big Cedar | 103P007 | unknown | 2016 | R
BCTS | !Planningb--TEbc032 | 14 | 5950 | Big Cedar | 103P007 | unknown | 2016 | R
BCTS | !Planningb--TEbc033 | 19.5 | 12105 | Big Cedar | 103P007 | unknown | 2016 | R
BCTS | !Planningb--TEbc034 | 7.7 | 3285 | Big Cedar | 103P017 | unknown | 2016 | R
BCTS | !Planningb--TEbc043 | 29.8 | 14155 | Big Cedar | 103P007 | unknown | 2015 | R
BCTS | !Planningb--TEbc052 | 18.4 | 7500 | Big Cedar | 103P007 | unknown | 2014 | R
BCTS | !Planningb--TEbc053 | 19.3 | 7500 | Big Cedar | 103P007 | unknown | 2014 | R
BCTS | !Planningb--TEsa002 | 19.2 | 3813 | Sandur | 103I048 | unknown | 2015 | W
BCTS | !Planningb--TEsa003 | 24.1 | 4787 | Sandur | 103I048 | unknown | 2015 | W
BCTS | !Planningb--TEth001 | 15.1 | 6400 | Thunderbird | 103I047 | unknown | 2016 | R
BCTS | !Planningb--TEth007 | 6.4 | 2700 | Thunderbird | 103I048 | unknown | 2016 | R
BCTS | !Planningb--TEth008 | 22.2 | 4950 | Thunderbird | 103I047 | unknown | 2015 | R
BCTS | !Planningb--TEth022 | 16 | 6800 | Thunderbird | 103I048 | unknown | 2015 | R
BCTS | !Planningb--TEth027 | 5.5 | 2800 | Thunderbird | 103I048 | unknown | 2016 | R
BCTS | !Planningb--TEth028 | 12.2 | 3300 | Thunderbird | 103I048 | unknown | 2016 | R
BCTS | !Planningb--TEth029 | 26.9 | 10200 | Thunderbird | 103I047 | unknown | 2015 | R
BCTS | !Planningb--TEth030 | 29.2 | 8500 | Thunderbird | 103I037 | unknown | 2016 | R
BCTS | !Planningb--TEth032 | 5.6 | 2600 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | !Planningb--TEth033 | 8.3 | 3200 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | !Planningb--TEth034 | 9.1 | 3000 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | !Planningb--TEth037 | 5.6 | 2200 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | A90582--TEbc005 | 49.4 | 23152 | Big Cedar | 103P007 | unknown | 2014 | W
BCTS | A90582--TEbc045 | 15.7 | 6457 | Big Cedar | 103P007 | unknown | 2014 | W
BCTS | A80642--1 | 20.4 | 12888 | Skeena West | 103I089 | unknown | 2014 | W
BCTS | A90581--TEsw049 | 62 | 24813 | Skeena West | 103I079 | unknown | 2014 | W
BCTS | A50591--1 | 21.7 | 12746 | Thunderbird | 103I047 | unknown | 2015 | W
BCTS | TEsw047 | 39.5 | 15800 | Skeena West | 103I079 | unknown | 2017 | R
BCTS | TEsw027 | 19.2 | 7800 | Skeena West | 103I089 | unknown | 2017 | R
BCTS | TEth031 | 9.7 | 4000 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth036 | 5.5 | 4500 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth035 | 5.4 | 2700 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | A89837--1 | 96.3 | 24627 | Douglas Creek | 103I087 | unknown | 2014 | F
442999
| Total volume identified: | 442999
| Annual Allocation within Kalum TSA: | 88228
| Allocation X 5 years: | 441140
| Years of supply: | 5
Note on B48: Rick: A&A: 13052 m3 allocation BCTS: 88228 CTR: 244037 KVL: 14454 KFP: 14454