## Sheet1
Date of Last Update: November 4th 2015 |  |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA
Updated by: Mark Reiter
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A79852 TEsw048 | 42.6449 | 16125 | New Skeena West | 103I079 | All | 2016 | C
BCTS | A93496-TEbc005, TEbc045 | 65.1 | 29496 | Big Cedar | 103P007 | All | 2016 | C
BCTS | A80642--1 | 20 | 12635 | Skeena West | 103I089 | All | 2016 | C
BCTS | A89837--1 | 83.2 | 24654 | Rosswood / Leanto Ck | 103I087 | All | 2016 | F
BCTS | A64102--1 | 40.4 | 19875 | Williams Creek Area | 103I049 | All | 2020 | F
BCTS | A78680--TEsa002 | 55.9 | 5500 | Sandur | 103I0048 | All | 2020 | F
BCTS | TEth001 | 33.3 | 6400 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth005 | 0 | 2570 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth007 | 0 | 2700 | Thunderbird | 103I048 | unknown | 2017 | R
BCTS | TEth027 | 5.4944 | 2335.12 | Thunderbird | 103I048 | unknown | 2017 | R
BCTS | TEth028 | 12.1547 | 3300 | Thunderbird | 103I048 | unknown | 2017 | R
BCTS | TEth030 | 20 | 8500 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth031 | 9.7 | 4000 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth032 | 5.5886 | 2375.155 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth033 | 8.2527 | 3200 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth034 | 9.1 | 3400 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth035 | 5.4 | 2295 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth037 | 5.6415 | 2200 | Thunderbird | 103I037 | unknown | 2017 | R
BCTS | TEth038 | 7.6 | 1515 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth039 | 13.7 | 5822.5 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth040 | 11.7 | 4972.5 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEth042 | 14.1 | 5992.5 | Thunderbird | 103I047 | unknown | 2017 | R
BCTS | TEbc011 | 48.3102 | 20531.835 | Big Cedar | 103I097 | unknown | 2017 | R
BCTS | TEbc017 | 40 | 15000 | Big Cedar | 103P017 | unknown | 2017 | R
BCTS | TEbc020 | 27.4 | 14984.8828 | Big Cedar | 103P007 | unknown | 2018 | R
BCTS | TEbc029 | 19.5 | 6188 | Big Cedar | 103P007 | unknown | 2018 | R
BCTS | TEbc031 | 33 | 14025 | Big Cedar | 103P017 | unknown | 2018 | R
BCTS | TEbc032 | 14.0063 | 5952.6775 | Big Cedar | 103P007 | unknown | 2018 | R
BCTS | TEbc033 | 19.4716 | 8275.43 | Big Cedar | 103P007 | unknown | 2018 | R
BCTS | TEbc034 | 7.4 | 3285 | Big Cedar | 103P007 | unknown | 2018 | R
BCTS | TEbc044 | 46.9 | 19932.5 | Big Cedar | 103P017 | unknown | 2018 | R
BCTS | TEbc055 | 16.3 | 6927.5 | Big Cedar | 103P017 | unknown | 2018 | R
BCTS | TEbc056 | 22.8 | 9261 | Big Cedar | 103P017 | unknown | 2018 | R
BCTS | TEbc057 | 29.9 | 12707.5 | Bi Cedar | 103P017 | unknown | 2018 | R
BCTS | TEbc058 | 28.4 | 12070 | Big Cedar | 103P017 | unknown | 2019 | R
BCTS | TEbc059 | 21.6 | 9180 | Big Cedar | 103P007/ 103P017 | unknown | 2019 | R
BCTS | TEbc060 | 18.8 | 7990 | Big Cedar | 103P007 | unknown | 2019 | R
BCTS | TEbc061 | 72.4 | 42380 | Big Cedar | 103P007 | unknown | 2019 | R
BCTS | TEbc062 | 11 | 3814 | Big Cedar | 103P007 | unknown | 2019 | R
BCTS | TEbc063 | 11 | 4675 | Big Cedar | 103P007 | unknown | 2019 | R
BCTS | TEbc064 | 58.8 | 24990 | Big Cedar | 103P007 | unknown | 2020 | R
BCTS | TEbc065 | 25.2 | 10710 | Big Cedar | 103P007 | unknown | 2020 | R
BCTS | TEsw052 | 24 | 10200 | Skeena West | 103I079 | unknown | 2020 | R
BCTS | TEsw053 | 26 | 10000 | Skeena west | 103I079 | unknown | 2020 | R
BCTS | TEsw054 | 23.9 | 9000 | Skeena West | 103I079 | unknown | 2020 | R
BCTS | TEsw055 | 24.2 | 10137 | Skeena West | 103I079 | unknown | 2020 | R
Sub total
| Total volume identified: | 462080.1003
| Annual Allocation within Kalum TSA: | 88228
| Allocation X 5 years: | 441140
| Years of supply: | 5.2373
Note on B56: Rick: A&A: 13052 m3 allocation BCTS: 88228 CTR: 244037 KVL: 14454 KFP: 14454