## Sheet1
Date : October 20,2016 |  |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA
Updated by: Mark Reiter
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A79849-009 | 27 | 11989 | Kitnayakwa | 093L041 | ALL | 2017 | C
BCTS | A79849-016 | 41.4 | 27550 | Kitnayakwa | 093L041 | ALL | 2017 | C
BCTS | A86361-002 | 30 | 12477 | Kitnayakwa | 093L041 | ALL | 2017 | C
BCTS | A86361-005 | 22 | 9058 | Kitnayakwa | 093L041 | ALL | 2017 | C
BCTS | A86361-006 | 31 | 11989 | Kitnayakwa | 093L041 | ALL | 2017 | C
BCTS | A93663 TEki007 | 27 | 12825 | Kitanayakwa | 093L041 | ALL | 2017 | C
BCTS | A93663-TEki017 | 10.9 | 3575 | Kitanayakwa | 093L041 | ALL | 2017 | C
BCTS | A93663-TEki018 | 14.6602 | 5250 | Kitanayakwa | 093L041/042031/032 | ALL | 2017 | C
BCTS | A93662-TElm003 | 14.6916 | 11900 | Limonite | 093L041/093L051 | ALL | 2017 | C
BCTS | A79853 TEki022 | 32.2888 | 10875 | Kitanayakwa | 093L041/093L051 | unknown | 2017 | C
BCTS | A79853 TEki026 | 10.5238 | 6300 | Kitanayakwa | 093L041 | ALL | 2017 | C
BCTS | A79853 TElm066 | 64.7 | 19000 | Limonite | 93L051 | ALL | 2017 | F
BCTS | A64070-TEbc021 | 18.2663 | 6500 | Big Cedar | 103I096 | ALL | 2017 | F
BCTS | A64070-TEbc022 | 16.2326 | 6000 | Big Cedar | 103I096 | ALL | 2017 | F
BCTS | A64070-TEbc023 | 22 | 14726 | Big Cedar | 103I096 | ALL | 2017 | F
BCTS | A64070-TEbc024 | 23 | 9900 | Big Cedar | 103I096 | ALL | 2017 | F
BCTS | !PlanningC--TElm004 | 28.4728 | 13050 | Limonite | 093L051 | ALL | 2017 | F
BCTS | A94376 TEbc071 | 33.5 | 22130 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A94376 TEbc076 | 34.2 | 15942 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A94375 TEbc026 | 12.4 | 5058 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A94375 TEbc027 | 27.9 | 11300 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A93665 TElm008 | 30.4069 | 13500 | Limonite | 93L051 | ALL | 2018 | F
BCTS | A93665 TElm009 | 46.3705 | 21850 | Limonite | 93L051 | ALL | 2018 | F
BCTS | A93665 TElm010 | 31.9048 | 12900 | Limonite | 93L051 | ALL | 2018 | F
BCTS | A93664-TElm024 | 45.7421 | 17250 | Limonite | 93L041\93L051 | ALL | 2018 | F
BCTS | A93664-TElm025 | 21.0431 | 8400 | Limonite | 93L041 | ALL | 2018 | F
BCTS | A93664-TElm026 | 56.6 | 22149 | Limonite | 93L041 | ALL | 2018 | F
BCTS | A94373 TElm034 | 21.4 | 10456 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373 TElm027 | 37 | 18615 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373 TElm028 | 25.8 | 12947 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373 TElm029 | 20.7 | 11199 | Limonite | 93L051 | ALL | 2019 | F
BCTS | TEki023 | 24.6 | 9775 | Kitanayakwa | 93L041 | unknown | 2019 | R
BCTS | TEki024 | 7 | 2063 | Kitanayakwa | 93L041 | unknown | 2019 | R
BCTS | TEki025 | 6.5 | 2813 | Kitanayakwa | 93L041 | unknown | 2019 | R
BCTS | TElm004 | 28.5 | 16050 | Limonite | 93L051 | unknown | 2019 | R
BCTS | TElm011 | 43.6 | 16800 | Limonite | 93L051 | unknown | 2019 | R
BCTS | TElm014 | 32.3 | 11200 | Limonite | 93L051 | unknown | 2019 | R
BCTS | TElm030 | 74.7 | 37423 | Limonite | 93L051 | unknown | 2019 | R
BCTS | TElm033 | 43 | 22675 | Limonite | 93L051 | unknown | 2019 | R
BCTS | TElm055 | 42.6 | 15532 | Limonite | 93L051 | unknown | 2020 | R
BCTS | TElm063 | 25.2 | 12266 | Limonite | 93L051 | unknown | 2020 | R
BCTS | TEng005 | 39.3 | 15600 | No gold | 103I060 | unknown | 2020 | R
BCTS | TEng006 | 26.3 | 11050 | No gold | 103I060 | unknown | 2020 | R
BCTS | TEng007. | 45 | 21105 | No gold | 93L051 | unknown | 2020 | R
BCTS | TEng008. | 50.7 | 28363 | No gold | 93L051 | unknown | 2020 | R
BCTS | TElm015 | 43.4 | 19350 | No gold | 93L051 | unknown | 2021 | R
BCTS | TElm016 | 18.06 | 7200 | No gold | 93L051 | unknown | 2021 | R
BCTS | TElm017 | 10.9 | 4000 | No gold | 93L051 | unknown | 2021 | R
BCTS | TElm018 | 14.9 | 7200 | No gold | 93L051 | unknown | 2021 | R
BCTS | TElm019 | 13.4 | 5200 | No gold | 103I060 | unknown | 2021 | R
BCTS | TEbc066 | 17.2 | 6949 | Big Cedar | 103I096 | unknown | 2021 | R
BCTS | TEbc067 | 13.4 | 3511 | Big Cedar | 103I096 | unknown | 2021 | R
| Total volume identified: | 672785
| Annual Allocation withinCascadia TSA: | 121941
| Allocation X 5 years: | 609705
| Years of supply: | 5.5173