## Sheet1
Date : October 25, 2017 |  |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA 2018-2022
Updated by: Mark Reiter
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A79853 TEki022 | 26.5 | 12381 | Kitanayakwa | 093L041/093L051 | ALL | 2018 | C
BCTS | A79853 TEki026 | 14.3 | 10099 | Kitanayakwa | 093L041 | ALL | 2018 | C
BCTS | A79853 TElm066 | 64.7 | 19000 | Limonite | 93L051 | ALL | 2018 | C
BCTS | A64070-TEbc021 | 18.2663 | 6500 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A64070-TEbc022 | 16.2326 | 6000 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A64070-TEbc023 | 22 | 14726 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A64070-TEbc024 | 23 | 9900 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | !PlanningC--TElm004 | 28.4728 | 13050 | Limonite | 093L051 | ALL | 2018 | F
BCTS | A64070 TEbc071 | 33.5 | 22130 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A64070 TEbc076 | 34.2 | 15942 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A94375 TEbc026 | 12.4 | 5058 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A94375 TEbc027 | 27.9 | 11300 | Big Cedar | 103I096 | ALL | 2018 | F
BCTS | A93665 TElm008 | 30.4069 | 13500 | Limonite | 93L051 | ALL | 2018 | F
BCTS | A93665 TElm009 | 46.3705 | 21850 | Limonite | 93L051 | ALL | 2018 | F
BCTS | A93665 TElm010 | 31.9048 | 12900 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373 TElm034 | 21.4 | 10456 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373- Telm027 | 34.4 | 16962 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A94373- Telm028 | 44.6 | 22824 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A95419-Telm030 | 68.9 | 37423 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A95419-Telm011 | 43.6 | 16800 | Limonite | 93L051 | ALL | 2019 | F
BCTS | A95645 TEng006 | 26.3 | 16022 | No Gold | 93L051 | ALL | 2020 | F
BCTS | A95645 TEng005 | 39.3 | 15390 | No Gold | 93L051 | ALL | 2020 | F
BCTS | A95750 A80876-1 | 49.6 | 21105 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A95750,TElm015 | 43.5 | 19350 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A95750 TElm016 | 18.6 | 7200 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A95750 TElm017 | 10.9 | 4000 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A95750 TElm018 | 14.9 | 7200 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A95750-Telm019 | 13.4 | 5200 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A85651 TElm004 | 28.5 | 8688 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A85651 TElm054 | 28.3 | 11107 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A85651 TElm014 | 32.3 | 11200 | Limonite | 93L051 | ALL | 2020 | F
BCTS | A85651 TEki023 | 24.6 | 6684 | Kitanayakwa | 93L051 | ALL | 2020 | F
BCTS | A85651-TEki024 | 7.1 | 2063 | Kitanayakwa | 93L041 | ALL | 2020 | F
BCTS | A95587 TElm064 | 136.5 | 56362 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A95647 TEki027 | 21.5 | 10620 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A95647 TEki034 | 21.5 | 10760 | Kitanayakwa | 93L032 | ALL | 2021 | F
BCTS | A95647 TEKi036 | 18.8 | 7191 | Kitanayakwa | 93L032 | ALL | 2021 | F
BCTS | A94376 TEng007 | 29 | 13500 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A94376 TEng009 | 22.5 | 8437 | No Gold | 93L051 | ALL | 2021 | F
BCTS | A94376 TEng011 | 14.1 | 6720 | No Gold | 93L051 | ALL | 2021 | F
BCTS | A94376 TEng013 | 21.4 | 9630 | No Gold | 93L051 | ALL | 2022 | F
BCTS | TElm029 | 40.1 | 20050 | Limonite | 93L051 | ALL | 2022 | R
BCTS | TElm033 | 43 | 22675 | Limonite | 93L051 | ALL | 2022 | R
BCTS | TElm050 | 58.3 | 32114 | Limonite | 93L051 | ALL | 2022 | R
BCTS | TElm052 | 48.5 | 12788 | Limonite | 93L051 | ALL | 2022 | R
BCTS | TElm053 | 58.3 | 20959 | Kitanayakwa | 93L041 | ALL | 2022 | R
BCTS | TElm055 | 50.5 | 15532 | Limonite | 93L051 | ALL | 2022 | R
681348
| Total volume identified: | 681348
| Annual Allocation within Cascadia TSA: | 121941
| Allocation X 5 years: | 609705
| Years of supply: | 5.5875