## 2017
Date of Last Update: | 2017-10-30 |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2018-2022
Updated by: | Mark Reiter
"Licencee" | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A64102--1 | 40.4 | 19875 | Williams Creek Area | 103I049 | summer | 2018 | C
BCTS | A94565 TEbc029 | 20.9 | 6188 | Big Cedar | 103P007/17 | ALL | 2018 | F
BCTS | A94565 TEbc031 | 30.23 | 14104 | Big Cedar | 103P017 | ALL | 2018 | F
BCTS | A94565 TEbc032 | 11.14 | 5950 | Big Cedar | 103P007 | ALL | 2018 | F
BCTS | A94565 TEbc033 | 23.52 | 12105 | Big Cedar | 103P007/17 | ALL | 2018 | F
BCTS | A93496-TEbc005 | 44.1 | 24101 | Big Cedar | 103P007 | ALL | 2018 | F
BCTS | A93496-TEbc045 | 11.6 | 5395 | Big Cedar | 103P007 | ALL | 2018 | F
BCTS | A78680--TEsa002 | 51.4 | 16846 | Sandur | 103I0048 | ALL | 2019 | F
BCTS | A95864 TEsw056 | 27.1 | 11096 | Skeena West | 103i079 | ALL | 2018 | F
BCTS | A95864 TEsw057 | 11.4 | 4600 | Skeena West | 103I079 | ALL | 2018 | F
BCTS | A95864 TEsw058 | 33.3 | 15264 | Skeena West | 103I079 | ALL | 2018 | F
BCTS | A95864 -A80642-1 | 20 | 9635 | Skeena West | 103I089 | ALL | 2018 | F
BCTS | A95770 TEbc061 | 72.4 | 42380 | Big Cedar | 103P007 | ALL | 2019 | F
BCTS | A95770 TEbc080 | 23.1 | 10276 | Big Cedar | 103P007 | ALL | 2019 | F
BCTS | A85649-TEsw016 | 29.8 | 10006 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A85649-TEsw017 | 31.5 | 16696 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A85649-TEsw051 | 11.6 | 5901 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | A95771 TEth007 | 12.6 | 4800 | Thunderbird | 103I048 | ALL | 2018 | F
BCTS | A95771 TEth027 | 5.4944 | 2800 | Thunderbird | 103I048 | ALL | 2018 | F
BCTS | A95771 TEth028 | 12.1547 | 3300 | Thunderbird | 103I048 | ALL | 2018 | F
BCTS | A79851 TEsw022 | 9.2 | 3597 | Skeena West | 103I089 | ALL | 2018 | F
BCTS | A79851 TEsw030 | 39.2 | 18315 | Skeena West | 103I089 | ALL | 2021 | F
BCTS | A95769 TEbc044 | 46.9 | 19932.5 | Big Cedar | 103P017 | ALL | 2021 | F
BCTS | A95103 TEbc055 | 23.9 | 11070 | Big Cedar | 103P018 | ALL | 2021 | F
BCTS | A95103 TEbc056 | 17.9 | 4937 | Big Cedar | 103P019 | ALL | 2021 | F
BCTS | A90583 TEsw025 | 15.8 | 7491 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | TEsw050 | 32.7 | 13701 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | TEsw054 | 23.9 | 12203 | Skeena West | 103I079 | ALL | 2019 | R
BCTS | TEsw055 | 24.2 | 10137 | Skeena West | 103I079 | ALL | 2019 | R
BCTS | TEkz002 | 31.1 | 22080 | Copper Rivert | 103I058 | ALL | 2020 | R
BCTS | TEkz003 | 13.6 | 5548 | Copper Rivert | 103I058 | ALL | 2020 | R
BCTS | TEro003 | 20.7 | 7085 | Glacier Creek | 103I067 | ALL | 2020 | R
BCTS | TEbc057 | 29.9 | 15385 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | TEbc058 | 28.4 | 12009 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | TEbc017 | 40 | 15000 | Big Cedar | 103P018 | ALL | 2022 | R
BCTS | TEbc059 | 0 | 19003 | Big Cedar | 103P017 | ALL | 2022 | R
BCTS | TEbc060 | 18.8 | 11193 | Big Cedar | 103P019 | ALL | 2022 | R
BCTS | TEbc081 | 42.7 | 15854 | Big Cedar | 103P007 | ALL | 2022 | R
BCTS | TElm045 | 42.6 | 8000 | No Gold | 103I060 | ALL | 2022 | R
BCTS | TElm046 | 10.2 | 4768 | No Gold | 103I061 | ALL | 2022 | R
BCTS | TElm047 | 18.1 | 6909 | No Gold | 103I062 | ALL | 2022 | R
485535.5
| Total volume identified: | 485535.5
| Annual Allocation within Kalum TSA: | 88228
| Allocation X 5 years: | 441140
| Years of supply: | 5.5032
Note on B51: Rick: A&A: 13052 m3 allocation BCTS: 88228 CTR: 244037 KVL: 14454 KFP: 14454