## Sheet1
Date : October 29 2019 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA 2020-2024
Updated by: Kyle Krupop
"Licencee" | Timber Sale License | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A93665 | TElm008 | 30.4069 | 15693 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A93665 | TElm009 | 56.6 | 28397 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A93665 | TElm010 | 31.9048 | 17979 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A94373 | TElm027 | 34.4 | 16962 | Limonite | 93L051 | ALL | 2019 | C
BCTS | A94373 | TElm028 | 44.6 | 22824 | Limonite | 93L051 | ALL | 2019 | C
BCTS | A95419 | TElm030 | 68.9 | 37423 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A95419 | TElm011 | 43.6 | 16800 | Limonite | 93L051 | ALL | 2021 | W
BCTS | A95645 | TEng005 | 31 | 12801 | NoGold | 93L051 | ALL | 2020 | C
BCTS | A95645 | TEng006 | 23.8 | 13125 | NoGold | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm067 | 45.5 | 13249 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm015 | 25.7 | 11784 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm016 | 16.6 | 5199 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm017 | 9.5 | 5952 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm018 | 13.9 | 5159 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A95750 | TElm019 | 12.3 | 5646 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A85651 | TElm004 | 21.3 | 8688 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A85651 | TElm054 | 28.3 | 12950 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A85651 | TElm014 | 30 | 9008 | Limonite | 93L051 | ALL | 2020 | C
BCTS | A85651 | TEki023 | 14.9 | 6683 | Kitnayakwa | 93L051 | ALL | 2020 | C
BCTS | A85651 | TEki024 | 7.1 | 2592 | Kitnayakwa | 93L041 | ALL | 2020 | C
BCTS | A95587 | TElm064 | 95.5 | 44131 | Limonite | 93L051 | ALL | 2021 | C
BCTS | A95647 | TEki027 | 13.6 | 3807 | Kitnayakwa | 93L051 | ALL | 2021 | F
BCTS | A95647 | TEki034 | 19.4 | 10137 | Kitnayakwa | 93L032 | ALL | 2021 | F
BCTS | A95647 | TEKi036 | 14.1 | 6585 | Kitnayakwa | 93L032 | ALL | 2021 | F
BCTS | A94376 | TEng007 | 31.8 | 11631 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng009 | 15.4 | 4755 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng011 | 17.4 | 6299 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng013 | 20.3 | 6695 | NoGold | 93L051 | ALL | 2022 | F
BCTS | Unassigned | TEki009 | 17.7 | 7943 | Kitnayakwa | 93L051 | ALL | 2022 | F
BCTS | Unassigned | TEki016 | 36.5 | 27550 | Kitnayakwa | 93L051 | ALL | 2022 | F
BCTS | TA0551 | TEng018 | 62.9 | 26759 | NoGold | 93L051 | ALL | 2022 | F
BCTS | TA0475 | TElm053 | 55.9 | 31920 | Limonite | 93L041 | ALL | 2022 | F
BCTS | TA0475 | TElm055 | 36.3 | 17665 | Limonite | 93L051 | ALL | 2022 | F
BCTS | TA0475 | TElm060 | 33.8 | 21569 | Limonite | 93L051 | ALL | 2020 | F
BCTS | TA1011 | TEsm001 | 31.8 | 8485 | Stenstrom | 103P028 | ALL | 2023 | F
BCTS | Unassigned | TEsm002 | 50.1 | 13369 | Stenstrom | 103P028 | ALL | 2023 | F
BCTS | Unassigned | TEsm003 | 24.9 | 6644 | Stenstrom | 103P028 | ALL | 2023 | F
BCTS | Unassigned | TEbc077 | 36.3 | 17678 | Big Cedar | 103I096 | ALL | 2023 | R
BCTS | Unassigned | TEbc104 | 19.7 | 6895 | Big Cedar | 103I096 | ALL | 2023 | R
BCTS | Unassigned | TEbc040 | 41 | 11700 | Meadow | 103I096 | ALL | 2023 | R
BCTS | Unassigned | TEng08A | 11 | 4172 | NoGold | 93L051 | ALL | 2020 | F
BCTS | Unassigned | TElm033 | 43 | 22675 | Limonite | 93L051 | ALL | 2023 | R
BCTS | Unassigned | TEki032 | 16.5 | 5880 | Kitnayakwa | 93L032 | ALL | 2023 | R
BCTS | Unassigned | TEki033 | 23.1 | 8208 | Kitnayakwa | 93L032 | ALL | 2023 | R
BCTS | Unassigned | TEki031 | 14.3 | 5586 | Kitnayakwa | 93L032 | ALL | 2023 | R
BCTS | Unassigned | TEng012 | 42.8 | 20500 | NoGold | 93L061 | ALL | 2023 | R
BCTS | Unassigned | TEki041 | 26.1 | 9605 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TEki042 | 18.6 | 7310 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TEki044 | 34.3 | 18145 | Kitnayakwa | 93L051 | ALL | 2021 | R
|  | Total Volume |  | 663212
|  | Total volume identified: | 663212
|  | Annual Allocation within Cascadia TSA: | 121941
|  | Allocation X 5 years: | 609705
|  | Years of supply: | 5.4388