## Sheet1
Date of Last Update: |  | 2019-10-29 |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2020-2024
Updated by: |  | Kyle Krupop
"Licencee" | TSL | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A64102 | 1 | 40.4 | 19875 | Williams Creek Area | 103I049 | ALL | 2019 | C
BCTS | A78680 | TEsa002 | 51.4 | 12000 | Sandur | 103I0048 | ALL | 2021 | F
BCTS | A79851 | 1 | 20 | 10698 | Skeena West | 103I089 | ALL | 2019 | C
BCTS | A85649 | TEsw016 | 29.8 | 15178 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A85649 | TEsw046 | 13.7 | 6546 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A85649 | TEsw051 | 11.6 | 5901 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A95769 | TEbc044 | 30.1 | 19649 | Big Cedar | 103P017 | ALL | 2019 | F
BCTS | A95770 | TEbc059 | 19 | 12672 | Big Cedar | 103P007 | ALL | 2020 | F
BCTS | A95770 | TEbc061 | 70 | 42165 | Big Cedar | 103P007 | ALL | 2022 | F
BCTS | A95770 | TEbc080 | 15 | 7270 | Big Cedar | 103P007 | ALL | 2020 | F
BCTS | A95771 | TEth007 | 9.9 | 4639 | Thunderbird | 103I048 | ALL | 2019 | C
BCTS | A95771 | TEth027 | 14.7 | 4899 | Thunderbird | 103I048 | ALL | 2019 | C
BCTS | A95771 | TEth028 | 12.9 | 3573 | Thunderbird | 103I048 | ALL | 2019 | C
BCTS | Unassigned | TEbc006 | 38.5 | 14000 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc017 | 40 | 15000 | Big Cedar | 103P018 | ALL | 2022 | R
BCTS | Unassigned | TEbc057 | 29.9 | 15385 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | Unassigned | TEbc058 | 28.4 | 12009 | Big Cedar | 103P017 | ALL | 2021 | R
BCTS | TA0389 | TEbc060 | 20.4 | 11193 | Big Cedar | 103P019 | ALL | 2022 | C
BCTS | TA0389 | TEbc081 | 42.7 | 15854 | Big Cedar | 103P007 | ALL | 2022 | C
BCTS | Unassigned | TEkz002 | 31 | 22080 | Kleanza | 103I058 | ALL | 2021 | F
BCTS | TA0474 | TEkz003 | 13.9 | 7429 | Kleanza | 103I058 | ALL | 2021 | F
BCTS | TA0534 | TEsw012 | 27.4 | 15384 | Skeena West | 103I068 | ALL | 2020 | F
BCTS | TA0534 | TEsw033 | 20.9 | 11054 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | TA0535 | TEsw020 | 18 | 6466 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | TA0535 | TEsw032 | 26.7 | 14423 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | TA0535 | TEsw038 | 18.4 | 8111 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | TA0535 | TEsw044 | 5.8 | 2331 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | A90581 | TEsw045 | 34.5 | 16400 | Skeena West | 103I079 | ALL | 2021 | R
BCTS | A90581 | TEsw050 | 32.5 | 13707 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | Unassigned | TEsw052 | 24 | 12524 | Skeena West | 103I079 | ALL | 2023 | R
BCTS | A95864 | TEsw056 | 27.1 | 13819 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | A95864 | TEsw057 | 9.9 | 4402 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | A95864 | TEsw058 | 32.4 | 16256 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | TA0535 | TEsw043 | 11.3 | 4200 | Skeena West | 103I079 | ALL | 2020 | F
BCTS | Unassigned | TEth044 | 30.5 | 12810 | Thunderbird | 103I047 | All | 2022 | R
BCTS | Unassigned | TEsw064 | 41 | 20490 | Skeena West | 103I079 | All | 2021 | R
BCTS | Unassigned | TEsw065 | 25 | 9000 | Skeena West | 103I089 | All | 2021 | R
BCTS | Unassigned | TEbc084 | 16 | 8960 | Big Cedar | 103P007 | All | 2021 | R
BCTS | Unassigned | TEbc119 | 31.9 | 16864 | Big Cedar | 103P007 | All | 2021 | R
|  |  | Total | 485216
Annual Allocation within Kalum TSA: |  |  | 88228
Annual Allocation x 5 years |  |  | 441140
|  | Total volume identified: | 485216
|  | Years of supply: | 5.4996