## Sheet1
Date : October 29, 2020 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA 2021-2025
Updated by: Karyn Roseboom
"Licencee" | Timber Sale License | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A93665 | TElm010 | 31.9048 | 17979 | Limonite | 93L051 | ALL | 2021 | C
BCTS | A94373 | TElm027 | 34.4 | 16962 | Limonite | 93L051 | ALL | 2019 | C
BCTS | A94373 | TElm028 | 44.6 | 22824 | Limonite | 93L051 | ALL | 2019 | C
BCTS | A95419 | TElm030 | 68.9 | 37423 | Limonite | 93L051 | ALL | 2021 | F
BCTS | A95419 | TElm011 | 43.6 | 19969 | Limonite | 93L051 | ALL | 2021 | W
BCTS | Unassigned | TEbc074 | 14.5 | 5893 | Big Cedar | 103I096 | ALL | 2022 | R
BCTS | TA1597 | TEbc036 | 48.5 | 20612 | Sterling | 103I096/103P006 | ALL | 2022 | W
BCTS | A95647 | TEki027 | 13.6 | 3807 | Kitnayakwa | 93L051 | ALL | 2021 | C
BCTS | A95647 | TEki034 | 31.3 | 10137 | Kitnayakwa | 93L032 | ALL | 2021 | C
BCTS | A95647 | TEKi036 | 18.8 | 6347 | Kitnayakwa | 93L032 | ALL | 2021 | C
BCTS | A94376 | TEng007 | 31.8 | 11631 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng009 | 15.4 | 4755 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng011 | 17.4 | 6299 | NoGold | 93L051 | ALL | 2021 | F
BCTS | A94376 | TEng013 | 20.3 | 6695 | NoGold | 93L051 | ALL | 2022 | F
BCTS | TA1271 | TEki009 | 17.7 | 7943 | Kitnayakwa | 93L051 | ALL | 2022 | C
BCTS | TA1271 | TEki016 | 36.5 | 27550 | Kitnayakwa | 93L051 | ALL | 2022 | C
BCTS | TA0551 | TEng018 | 76.9 | 26759 | NoGold | 93L051 | ALL | 2022 | C
BCTS | TA0475 | TElm053 | 55.9 | 31920 | Limonite | 93L041 | ALL | 2022 | F
BCTS | TA0475 | TElm055 | 36.3 | 17665 | Limonite | 93L051 | ALL | 2022 | F
BCTS | TA0475 | TElm060 | 33.8 | 21569 | Limonite | 93L051 | ALL | 2020 | F
BCTS | TA1011 | TEsm001 | 31.8 | 8485 | Stenstrom | 103P028 | ALL | 2023 | W
BCTS | Unassigned | TElm070 | 65 | 17133 | Limonite | 093L051 | ALL | 2023 | P
BCTS | Unassigned | TEbc077 | 38.5 | 15400 | Big Cedar | 103I096 | ALL | 2023 | W
BCTS | Unassigned | TEbc104 | 35 | 15390 | Big Cedar | 103I096 | ALL | 2023 | W
BCTS | Unassigned | TEbc040 | 41 | 11700 | Meadow | 103I096 | ALL | 2023 | R
BCTS | A94376 | TEng08A | 11.1 | 5086 | Kleanza | 93L051 | ALL | 2022 | F
BCTS | TA1595 | TEng014 | 47 | 11000 | NoGold | 093L061 | ALL | 2022 | W
BCTS | Unassigned | TElm033 | 43 | 14548 | Limonite | 93L051 | ALL | 2023 | R
BCTS | TA1594 | TEki032 | 48.5 | 35596 | Kitnayakwa | 93L032 | ALL | 2023 | R
BCTS | Unassigned | TEng012 | 39.7 | 10000 | NoGold | 93L061 | ALL | 2023 | R
BCTS | Unassigned | TEng008 | 20.9 | 8360 | NoGold | 93L051 | ALL | 2024 | W
BCTS | Unassigned | TElm052 | 44.1 | 12788 | Limonite | 093L051 | ALL | 2025 | P
BCTS | Unassigned | TEki041 | 26.1 | 9605 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TEki042 | 18.6 | 7310 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TElm050 | 53.1 | 32114 | Limonite | 093L051 | ALL | 2026 | P
BCTS | Unassigned | TElm071 | 55.8 | 27900 | Limonite | 093L051 | ALL | 2026 | P
BCTS | Unassigned | TEbc114 | 30.1 | 11300 | Big Cedar | 103I097 | ALL | 2024 | P
BCTS | Unassigned | TEbc113 | 32.3 | 10500 | Big Cedar | 103I097 | ALL | 2024 | P
BCTS | TA1598 | TElm063 | 45 | 19152 | Limonite | 093L051 | ALL | 2022 | W
BCTS | A80876 | 2 | 45 | 19152 | Limonite | 093L051 | ALL | 2022 | W
|  | Total Volume |  | 627258
|  | Total volume identified: | 627258
|  | Annual Allocation within Cascadia TSA: | 116760
|  | Allocation X 5 years: | 583800
|  | Years of supply: | 5.3722