## Final Copy
Date of Last Update: Oct 29, 2020 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2021-2025
Updated by: Kirstin Eyolfson
"Licencee" | TSL | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A64102 | 1 | 40.4 | 19875 | Williams Creek Area | 103I049 | ALL | 2019 | C
BCTS | A78680 | TEsa002 | 51.4 | 8251 | Sandur | 103I048 | ALL | 2021 | F
BCTS | Unassigned | TEth030 | 20 | 8500 | Thunderbird | 103I037 | ALL | 2023 | R
BCTS | TA1269 | TEsw016 | 29.8 | 14949 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | TA1269 | TEsw017 | 31.5 | 15362 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | TA1269 | TEsw051 | 11.6 | 4691 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | Unassigned | TEth031 | 10 | 4000 | Thunderbird | 103I037 | ALL | 2023 | R
BCTS | A95770 | TEbc059 | 19 | 12672 | Big Cedar | 103P007 | ALL | 2020 | C
BCTS | A95770 | TEbc080 | 15 | 7270 | Big Cedar | 103P007 | ALL | 2020 | C
BCTS | Unassigned | TEbc090 | 25.4 | 10429 | Swansons | 103P007 | ALL | 2023 | F
BCTS | Unassigned | TEbc089 | 27.5 | 11437 | Swansons | 93I097 | ALL | 2023 | F
BCTS | TA1038 | TEbc098 | 14.5 | 5580 | Big Cedar | 103P007 | ALL | 2023 | F
BCTS | TA1105 | TEbc006 | 56.2 | 47877 | Big Cedar | 103P017 | ALL | 2021 | F
BCTS | TA1105 | TEbc017 | 46.9 | 32677 | Big Cedar | 103P018 | ALL | 2022 | F
BCTS | TA1038 | TEbc057 | 58.3 | 31626 | Big Cedar | 103P017 | ALL | 2021 | F
BCTS | Unassigned | TEbc011 | 48 | 16700 | Big Cedar | 103I097 | ALL | 2023 | F
BCTS | Unassigned | TEth005 | 8 | 2570 | Thunderbird | 103I037 | ALL | 2023 | F
BCTS | TA0474 | TEkz003 | 13.9 | 7429 | Kleanza | 103I058 | ALL | 2021 | C
BCTS | TA0534 | TEsw012 | 27.4 | 15384 | Skeena West | 103I068 | ALL | 2020 | C
BCTS | TA0534 | TEsw033 | 20.9 | 11054 | Skeena West | 103I079 | ALL | 2020 | C
BCTS | TA0535 | TEsw020 | 18 | 6466 | Skeena West | 103I079 | ALL | 2020 | C
BCTS | Unassigned | TEth001 | 21.7 | 8000 | Thunderbird | 103I047 | ALL | 2023 | F
BCTS | A90581 | TEsw045 | 34.5 | 10177 | Skeena West | 103I079 | ALL | 2021 | F
BCTS | A90581 | TEsw050 | 32.5 | 13707 | Skeena West | 103I079 | ALL | 2019 | F
BCTS | Unassigned | TEsw052 | 24 | 12524 | Skeena West | 103I079 | ALL | 2023 | R
BCTS | A95864 | TEsw056 | 27.1 | 13819 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | A95864 | TEsw057 | 9.9 | 4402 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | A95864 | TEsw058 | 32.4 | 16256 | Skeena West | 103I079 | ALL | 2019 | C
BCTS | Unassigned | TEth044 | 30.5 | 12810 | Thunderbird | 103I047 | All | 2022 | R
BCTS | Unassigned | TEsw064 | 41 | 20490 | Skeena West | 103I079 | All | 2021 | F
BCTS | Unassigned | TEbc084 | 16 | 8960 | Big Cedar | 103P007 | All | 2021 | R
BCTS | Unassigned | TEbc119 | 31.9 | 16864 | Big Cedar | 103P007 | All | 2021 | R
BCTS | Unassigned | TEsw028 | 17 | 6000 | Skeena West | 103I089 | All | 2024 | R
BCTS | Unassigned | TEsw054 | 24 | 11000 | Skeena West | 103I079 | All | 2024 | R
BCTS | Unassigned | TEsw053 | 28.3 | 13635 | Skeena West | 103I079 | All | 2024 | R
BCTS | Unassigned | TEbc112 | 60 | 21000 | Big Cedar | 103P007 | All | 2023 | R
BCTS | Unassigned | TEsw021 | 7.4 | 3000 | Skeena West | 103I089 | ALL | 2024 | R
|  |  | Total | 487443
Annual Allocation within Kalum TSA: |  |  | 88228
Annual Allocation x 5 years |  |  | 441140
|  | Total volume identified: | 487443
|  | Years of supply: | 5.5248