## Sheet1
Date : Nov 1, 2021 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Cascadia TSA 2021-2025
Updated by: Kirstin Eyolfson
"Licencee" | Timber Sale License | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | TA0475 | TElm053 | 55.9 | 28744 | Limonite | 93L041 | ALL | 2022 | F
BCTS | TA0475 | TElm055 | 36.3 | 13544 | Limonite | 93L051 | ALL | 2022 | F
BCTS | TA1594 | TEki032 | 48.5 | 35596 | Kitnayakwa | 93L032 | ALL | 2023 | F
BCTS | TA1595 | TEng014 | 54 | 31316 | NoGold | 093L061 | ALL | 2022 | F
BCTS | TA1596 | TEbc077 | 30.8 | 12515 | Big Cedar | 103I096 | ALL | 2023 | F
BCTS | TA1596 | TEbc104 | 33.5 | 13160 | Big Cedar | 103I096 | ALL | 2023 | F
BCTS | TA1597 | TEbc036 | 43.8 | 18436 | Sterling | 103I096/103P006 | ALL | 2022 | F
BCTS | TA1597 | TEbc040 | 34.8 | 9519 | Meadow | 103I096 | ALL | 2023 | F
BCTS | TA1598 | TElm063 | 84.9 | 35577 | Limonite | 093L051 | ALL | 2022 | F
BCTS | TA2019 | TEbc125 | 36.5 | 19160 | Big Cedar | 103I096 | ALL | 2023 | W
BCTS | TA2020 | TEbc114 | 27.9 | 10524 | Big Cedar | 103I097 | ALL | 2024 | W
BCTS | TA2020 | TEbc115 | 26.7 | 7270 | Big Cedar | 103I097 | ALL | 2023 | W
BCTS | TA2021 | TEng008 | 33.7 | 22682 | NoGold | 93L051 | ALL | 2024 | W
BCTS | TA2022 | TEbc128 | 30.8 | 12825 | Big Cedar | 103P006 | ALL | 2024 | W
BCTS | Unassigned | TEki041 | 26.1 | 9605 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TEki042 | 18.6 | 7310 | Kitnayakwa | 93L051 | ALL | 2021 | R
BCTS | Unassigned | TElm033 | 35.9 | 14548 | Limonite | 93L051 | ALL | 2023 | R
BCTS | Unassigned | TElm050 | 53.1 | 32114 | Limonite | 093L051 | ALL | 2026 | P
BCTS | Unassigned | TElm052 | 44.1 | 12788 | Limonite | 093L051 | ALL | 2025 | P
BCTS | Unassigned | TElm060 | 33.8 | 17399 | Limonite | 93L051 | ALL | 2023 | F
BCTS | Unassigned | TElm070 | 65.4 | 28453 | Limonite | 093L051 | ALL | 2023 | R
BCTS | TA1011 | TEsm002 | 38.4 | 26264 | Stenstrom | 103P028 | ALL | 2023 | F
BCTS | Unassigned | TEnh003 | 45.7 | 29402 | North Hirsch | 103I009 | ALL | 2024 | R
BCTS | Unassigned | A64088-3 | 25.1 | 10500 | North Hirsch | 103I009 | ALL | 2024 | R
BCTS | TA0537 | TEnh025 | 42.3 | 12632 | North Hirsch | 103I009 | ALL | 2022 | F
BCTS | Unassigned | TEnh021 | 18 | 8765 | North Hirsch | 103I009 | ALL | 2024 | R
BCTS | Unassigned | TEnh017 | 14 | 10046 | North Hirsch | 103I009 | ALL | 2026 | R
BCTS | TA0541 | TEnh001 | 52.6 | 30428 | North Hirsch | 103I008 | ALL | 2022 | F
BCTS | Unassigned | TElm051 | 14 | 5388 | Limonite | 093L051 | ALL | 2025 | R
BCTS | Unassigned | TEki029 | 40.1 | 20050 | Kitnayakwa | 093L041 | ALL | 2026 | R
BCTS | Unassigned | A64086-2 | 23 | 8182 | North Hirsch |  | ALL | 2024 | R
BCTS | Unassigned | TEki044 | 28.9 | 17166 | Kitnayakwa | 093L041 | ALL | 2024 | R
BCTS | Unassigned | TEnh020 | 18.1 | 9360 | North Hirsch | 103I009 | ALL | 2025 | R
BCTS | Unassigned | TEki046 | 34.4 | 13689 | Kitnayakwa | 093L041/103I050 | ALL | 2024 | R
BCTS | Unassigned | TEki047 | 28.9 | 11975 | Kitnayakwa | 093L041 | ALL | 2025 | R
BCTS | Unassigned | TEki048 | 41.8 | 16720 | Kitnayakwa | 093L041 | ALL | 2025 | R
BCTS | Unassigned | TEnh009 | 34.7 | 13600 | North Hirsch | 103I009 | ALL | 2024 | R
BCTS | Unassigned | TElm056 | 14.5 | 6935 | Limonite | 093L051 | ALL | 2025 | R
|  | Total Volume |  | 644187
|  | Total volume identified: | 644187
|  | Annual Allocation within Cascadia TSA: | 116760
|  | Allocation X 5 years: | 583800
|  | Years of supply: | 5.5172