## Final Copy
Date of Last Update: Nov 1, 2021 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2021-2025
Updated by: Kirstin Eyolfson
"Licencee" | TSL | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A78680 | TEsa002 | 51.4 | 8251 | Sandur | 103I048 | ALL | 2023 | F
BCTS | A90581 | TEsw045 | 34.5 | 10177 | Skeena West | 103I079 | ALL | 2023 | F
BCTS | A90581 | TEsw050 | 32.5 | 13707 | Skeena West | 103I079 | ALL | 2023 | F
BCTS | TA1105 | TEbc006 | 56.2 | 47877 | Big Cedar | 103P017 | ALL | 2023 | F
BCTS | TA1105 | TEbc017 | 46.9 | 32677 | Big Cedar | 103P018 | ALL | 2024 | F
BCTS | TA1269 | TEsw016 | 29.8 | 15559 | Skeena West | 103I079 | ALL | 2022 | F
BCTS | TA1269 | TEsw017 | 31.5 | 16409 | Skeena West | 103I079 | ALL | 2022 | F
BCTS | TA1269 | TEsw051 | 11.6 | 4691 | Skeena West | 103I079 | ALL | 2022 | F
BCTS | TA1269 | TEsw064 | 41 | 15612 | Skeena West | 103I079 | ALL | 2022 | F
BCTS | TA1561 | TEbc011 | 48.3 | 37837 | Big Cedar | 103I097 | ALL | 2023 | F
BCTS | TA1561 | TEbc089 | 27.5 | 16078 | Swansons | 103I097 | ALL | 2023 | F
BCTS | TA1561 | TEbc090 | 26 | 14731 | Swansons | 103P007 | ALL | 2023 | F
BCTS | TA1562 | TEbc098 | 14.5 | 11415 | Big Cedar | 103P007 | ALL | 2023 | F
BCTS | TA1563 | TEth001 | 24.2 | 10533 | Thunderbird | 103I047 | ALL | 2022 | F
BCTS | TA1563 | TEth005 | 4.1 | 1956 | Thunderbird | 103I037 | ALL | 2022 | F
BCTS | TA1563 | TEth030 | 16 | 5379 | Thunderbird | 103I037 | ALL | 2022 | F
BCTS | TA1563 | TEth031 | 9.7 | 4831 | Thunderbird | 103I037 | ALL | 2022 | F
BCTS | TA1885 | 1 | 40.4 | 19875 | Williams Creek Area | 103I049 | ALL | 2022 | F
BCTS | Unassigned | TEbc084 | 16 | 8960 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEbc112 | 65.9 | 27678 | Big Cedar | 103P007 | ALL | 2024 | W
BCTS | Unassigned | TEbc119 | 31.9 | 16864 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEbc120 | 30.2 | 12617 | Big Cedar | 103P007 | ALL | 2024 | W
BCTS | Unassigned | TEsw021 | 10.2 | 4080 | Skeena West | 103I089 | ALL | 2023 | W
BCTS | Unassigned | TEsw028 | 19.6 | 7644 | Skeena West | 103I089 | ALL | 2023 | W
BCTS | Unassigned | TEsw052 | 24 | 12524 | Skeena West | 103I079 | ALL | 2025 | R
BCTS | Unassigned | TEsw053 | 28.3 | 13635 | Skeena West | 103I079 | ALL | 2025 | R
BCTS | Unassigned | TEsw054 | 8.5 | 4037 | Skeena West | 103I079 | ALL | 2024 | W
BCTS | Unassigned | TEbc110 | 23 | 11190 | Big Cedar | 103I097 | ALL | 2025 | R
BCTS | Unassigned | TEbc111 | 37 | 25635 | Big Cedar | 103I097 | ALL | 2025 | R
BCTS | Unassigned | TEsw011 | 28 | 6000 | Skeena West | 103I079 | ALL | 2025 | R
BCTS | Unassigned | TEsw027 | 17 | 7800 | Skeena West | 103I089 | ALL | 2025 | R
BCTS | Unassigned | TEth045 | 32.8 | 23684 | Thunderbird | 103I047 | ALL | 2026 | R
BCTS | Unassigned | TEsw066 | 13.5 | 10302 | Skeena West | 103I089 | ALL | 2026 | R
|  |  | Total | 480245
Annual Allocation within Kalum TSA: |  |  | 88228
Annual Allocation x 5 years |  |  | 441140
|  | Total volume identified: | 480245
|  | Years of supply: | 5.4432