## Final Copy
Date of Last Update: October 31, 2022 |  |  |  |  | BC Timber Sales Skeena 5 Year Plan Kalum TSA 2022-2026
Updated by: Kirstin Eyolfson
"Licencee" | TSL | Block ID | Merch Area (ha) | Volume (m3) | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
BCTS | A78680 | TEsa002 | 51.4 | 16839 | Sandur | 103I048 | ALL | 2024 | F
BCTS | A90581 | TEsw045 | 34.5 | 10177 | Skeena West | 103I079 | ALL | 2023 | F
BCTS | A90581 | TEsw050 | 32.5 | 13707 | Skeena West | 103I079 | ALL | 2023 | F
BCTS | TA1105 | TEbc006 | 56.2 | 41080 | Big Cedar | 103P017 | ALL | 2023 | F
BCTS | TA1561 | TEbc011 | 48.3 | 37837 | Big Cedar | 103I097 | ALL | 2023 | F
BCTS | TA1561 | TEbc089 | 27.5 | 16078 | Swansons | 103I097 | ALL | 2023 | F
BCTS | TA1561 | TEbc090 | 26 | 14731 | Swansons | 103P007 | ALL | 2023 | F
BCTS | TA1667 | TEsw064 | 41 | 15612 | Skeena West | 103I079 | ALL | 2025 | F
BCTS | TA2070 | TEbc112 | 61.5 | 27109 | Big Cedar | 103P007 | ALL | 2024 | F
BCTS | TA2070 | TEbc120 | 31.2 | 11796 | Big Cedar | 103P007 | ALL | 2024 | F
BCTS | TA2071 | TEsw054 | 8.5 | 4037 | Skeena West | 103I079 | ALL | 2024 | W
BCTS | TA2071 | TEsw061 | 18.3 | 6732 | Skeena West | 103I079 | ALL | 2026 | R
BCTS | TA2090 | TEbc017 | 46.9 | 32677 | Big Cedar | 103P018 | ALL | 2024 | F
BCTS | TA2090 | TEbc098 | 14.5 | 11415 | Big Cedar | 103P007 | ALL | 2023 | F
BCTS | Unassigned | TEbc083 | 15.5 | 5436 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEbc084 | 16 | 8960 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEbc086 | 80.2 | 22538 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEbc110 | 23 | 11190 | Big Cedar | 103I097 | ALL | 2025 | R
BCTS | Unassigned | TEbc111 | 37 | 25635 | Big Cedar | 103I097 | ALL | 2025 | R
BCTS | Unassigned | TEbc119 | 31.9 | 16864 | Big Cedar | 103P007 | ALL | 2025 | R
BCTS | Unassigned | TEsw021 | 10.2 | 4080 | Skeena West | 103I089 | ALL | 2025 | F
BCTS | Unassigned | TEsw028 | 19.6 | 7644 | Skeena West | 103I089 | ALL | 2025 | F
BCTS | Unassigned | TEsw052 | 24 | 12524 | Skeena West | 103I079 | ALL | 2025 | R
BCTS | Unassigned | TEsw053 | 28.3 | 13635 | Skeena West | 103I079 | ALL | 2025 | R
BCTS | Unassigned | TEsw059 | 20.6 | 8957 | Skeena West | 103I079 | ALL | 2026 | R
BCTS | Unassigned | TEsw060 | 21.1 | 8050 | Skeena West | 103I079 | ALL | 2026 | R
BCTS | Unassigned | TEbc094 | 30.7 | 9018 | Swansons | 103I097 | ALL | 2026 | R
BCTS | Unassigned | TEbc095 | 39.9 | 10950 | Swansons | 93I097 | ALL | 2026 | R
BCTS | Unassigned | TEbc096 | 32.8 | 9165 | Swansons | 93I097 | ALL | 2026 | R
BCTS | Unassigned | TEbc097 | 9.5 | 2599 | Swansons | 93I097 | ALL | 2026 | R
BCTS | Unassigned | TEbc010 | 40 | 16000 | Big Cedar | 103P007 | ALL | 2027 | R
BCTS | Unassigned | TEbc121 | 46.2 | 16744 | Big Cedar | 103P007 | ALL | 2027 | R
BCTS | Unassigned | Tebc132 | 8.8 | 1420 | Big Cedar | 103P007 | ALL | 2027 | R
BCTS | Unassigned | TEbc133 | 39 | 14475 | Big Cedar | 103P007 | ALL | 2027 | R
|  |  | Total | 485711
Annual Allocation within Kalum TSA: |  |  | 88228
Annual Allocation x 5 years |  |  | 441140
|  | Total volume identified: | 485711
|  | Years of supply: | 5.5052