## Sheet1
Date of Last Update: |  | 2018-11-15 |  |  |  | Coast Tsimshan Resources LP
Updated by: |  | J.Crawford |  |  |  |  | Tenure FL A16835
FID | LOGYEAR | STATUS | BLOCKNO | OWNER | CP | Harvest | Hectares | Comments | Location | Mapsheet | Volume | ProjLogYr | Season
0 | 0 | P | C16014 | A16835 |  | Proposed | 31.7374 |  | Exstew | 103I045 | 13472.5 | 2020 | Summer
1 | 0 | P | R79045 | A16835 |  | Proposed | 35.6589 |  | Kleanza | 103I060 | 15172.5 | 2021 | Summer
2 | 0 | P | R77565 | A16835 | 427 | Issued | 71.6147 |  | Kleanza | 103I060 | 32655.4 | 2022 | Summer
3 | 0 | P | R81209 | A16835 |  | Proposed | 15.6784 |  | Kleanza | 103I060 | 6659.75 | 2022 | Summer
4 | 0 | P | R80107 | A16835 |  | Proposed | 5.4801 |  | Kleanza | 103I060 | 2337.5 | 2021 | Summer
5 | 0 | P | R80119 | A16835 |  | Proposed | 36.4527 |  | Kleanza | 103I060 | 15512.5 | 2021 | Summer
6 | 0 | P | R80117 | A16835 |  | Proposed | 14.2846 |  | Kleanza | 103I060 | 6077.5 | 2021 | Summer
7 | 0 | P | R77944 | A16835 |  | Proposed | 55.58 | Not Harvested | Kleanza | 103I060 | 23630 | 2021 | Summer
8 | 0 | P | S83116 | A16835 | 527 | Proposed | 14.9276 |  | Singlehurst | 103I069 | 6344 | 2021 | Summer
9 | 0 | P | G38225 | A16835 |  | Proposed | 31.4261 |  | Wesach | 103I077 | 13345 | 2020 | Summer
10 | 0 | P | H39125 | A16835 |  | Proposed | 9.1013 |  | Maroon | 103I077 | 6715 | 2019 | Summer
11 | 0 | P | G37125 | A16835 | 154 | Proposed | 27.1634 |  | Douglas | 103I087 | 11560 | 2022 | Summer
12 | 0 | P | G37303 | A16835 | 740 | Proposed | 23.8297 |  | Douglas | 103I087 | 10115 | 2020 | Summer
13 | 0 | P | G37114 | A16835 | 744 | Proposed | 3.3124 |  | Douglas | 103I087 | 993 | 2019 | Summer
14 | 0 | P | S83418 | A16835 |  | Proposed | 33.8699 |  | Singlehurst | 103I069 | 14394 | 2021 | Summer
15 | 0 | P | F34219 | A16835 | 840 | Retired | 56.2096 |  | Sterling | 103P006 | 17222 | 2019 | Summer
16 | 0 | P | F34211 | A16835 | 840 | Retired | 24.987 |  | Sterling | 103P006 | 9337 | 2019 | Summer
17 | 0 | P | C16561 | A16835 | 204 | Retired | 21.5603 |  | Exstew | 103I045 | 8440 | 2020 | Summer
18 | 0 | P | C16558 | A16835 | 204 | Retired | 7.7066 |  | Exstew | 103I045 | 4042.5 | 2020 | Summer
19 | 0 | P | R76119 | A16835 | 437 | Retired | 13.4088 |  | Kleanza | 103I059 | 5587.8 | 2022 | Summer
20 | 0 | P | R79311 | A16835 | 436 | Retired | 19.3925 |  | Kleanza | 103I060 | 9416.3 | 2019 | Summer
21 | 0 | P | T87035 | A16835 | 541 | Proposed | 39.7341 |  | Legate | 103I079 | 16872.5 | 2022 | Summer
22 | 0 | P | T87053 | A16835 | 193 | Proposed | 36.8443 |  | Legate | 103I079 | 15640 | 2020 | Summer
23 | 0 | P | T87311 | A16835 |  | Proposed | 32.7263 |  | Legate | 103I080 | 18144 | 2021 | Summer
24 | 0 | P | S83206 | A16835 |  | Proposed | 14.834 |  | Chimdemash | 103I069 | 6344.2114 | 2021 | Summer
25 | 0 | P | C16551 | A16835 | 204 | Retired | 3.3558 |  | Exstew | 103I045 | 1293.7 | 2020 | Summer
26 | 0 | P | C16552 | A16835 | 204 | Retired | 1.4944 |  | Exstew | 103I045 | 735 | 2020 | Summer
27 | 0 | P | P67097 | A16835 | 335 | Retired | 21.4156 |  | Williams Creek | 103I039 | 14177.5 | 2018 | Summer
29 | 0 | P | P69107 | A16835 | 338 | Issued | 7.0111 |  | Williams Creek | 103I049 | 4417 | 2018 | Summer
30 | 0 | P | P69108 | A16835 | 338 | Issued | 20.2118 |  | Williams Creek | 103I039 | 12039.2 | 2018 | Summer
31 | 0 | P | P69109 | A16835 | 338 | Issued | 79.3953 |  | Williams Creek | 103I039 | 47322.4 | 2018 | Summer
32 | 0 | P | E27412 | A16835 | 206 | Retired | 13.4758 |  | Zymagotitz River | 103I057 | 8059 | 2018 | Summer
33 | 0 | P | E27411 | A16835 | 207 | Proposed | 61.6926 |  | Zymagotitz River | 103I057 | 36963 | 2019 | Summer
34 | 0 | P | G37205 | A16835 | 744 | Proposed | 13.0837 |  | Douglas | 103I087 | 3930 | 2022 | Summer
35 | 0 | P | P69312 | A16835 |  | Proposed | 10.0244 |  | Williams Creek | 103I039 | 4250 | 2021 | Summer
36 | 0 | P | P67078 | A16835 | 335 | Retired | 10.7889 |  | Williams Creek | 103I039 | 6445.8 | 2018 | Summer
37 | 0 | P | P67077 | A16835 | 335 | Retired | 34.0532 |  | Williams Creek | 103I039 | 22618.2 | 2018 | Summer
38 | 0 | P | T87034 | A16835 | 548 | Retired | 11.1354 |  | Legate | 103I079 | 2622 | 2021 | Summer
39 | 0 | P | G36301 | A16835 | 744 | Proposed | 96.9096 | Part logged by BCTS | Douglas | 103I087 | 27090 | 2020 | Summer
40 | 0 | P | S83209 | A16835 |  | Proposed | 19.8557 |  | Chimdemash | 103I069 | 6070 | 2018 | Summer
41 | 0 | P | H39142 | A16835 | 721 | Proposed | 16.257 |  | Maroon | 103I077 | 7370.3 | 2022 | Summer
42 | 0 | P | H39143 | A16835 | 721 | Proposed | 46.4197 |  | Maroon | 103I077 | 20028 | 2022 | Summer
43 | 0 | P | G38017 | A16835 |  | Proposed | 10.6903 |  | Wesach | 103I077 | 3210 | 2022 | Summer
47 | 0 | P | R77546 | A16835 | 441 | Retired | 2.1986 |  | Kleanza | 103I059 | 1245 | 2018 | Summer
48 | 0 | P | R77113 | A16835 | 441 | Retired | 16.0435 |  | Kleanza | 103I059 | 6750.7 | 2018 | Summer
49 | 0 | P | Q74211 | A16835 |  | Proposed | 2.9561 |  | North Copper | 103I058 | 1160 | 2018 | Summer
51 | 0 | P | Q74521 | A16835 | 444 | Issued | 2.2891 |  | North Copper | 103I059 | 1571 | 2018 | Summer
52 | 0 | P | H39206 | A16835 |  | Proposed | 5.6695 |  | Maroon | 103I077 | 2160 | 2019 | Summer
53 | 0 | P | H39033 | A16835 |  | Proposed | 8.0756 |  | Maroon | 103I077 | 3442.5 | 2019 | Summer
54 | 0 | P | R76049 | A16835 | 441 | Retired | 10.0233 |  | Kleanza | 103I059 | 5039 | 2018 | Summer
55 | 0 | P | Q74514 | A16835 | 444 | Issued | 2.0404 |  | Copper | 103I058 | 1242.4 | 2018 | Summer
56 | 0 | P | R77545 | A16835 | 443 | Proposed | 6.3809 |  | Kleanza | 103I060 | 2720 | 2019 | Summer
58 | 0 | P | R77751 | A16835 | 443 | Proposed | 6.7139 |  | Kleanza | 103I060 | 2847.5 | 2019 | Summer
59 | 0 | P | R77753 | A16835 | 442 | Proposed | 8.3834 |  | Kleanza | 103I060 | 3570 | 2021 | Summer
61 | 0 | P | H39216 | A16835 |  | Proposed | 35.0924 |  | Maroon | 103I077 | 14040 | 2019 | Summer
62 | 0 | P | R77549 | A16835 | 442 | Proposed | 8.4049 |  | Kleanza | 103I060 | 3570 | 2021 | Summer
63 | 0 | P | T86007 | A16835 | 549 | Proposed | 5.6213 |  | Legate | 103I079 | 2529.5914 | 2021 | Summer
64 | 0 | P | T86119 | A16835 | 549 | Proposed | 15.2609 |  | Legate | 103I079 | 6840 | 2018 | Summer
65 | 0 | P | G36046 | A16835 |  | Retired | 3.0535 |  | Clear Creek | 103I087 | 450 | 2020 | Summer
66 | 0 | P | S83211 | A16835 |  | Proposed | 9.5506 |  | Chimdemash | 103I069 | 4059 | 2021 | Summer
67 | 0 | P | S83212 | A16835 |  | Proposed | 4.0137 |  | Chimdemash | 103I069 | 1705 | 2021 | Summer
68 | 0 | P | S83213 | A16835 |  | Proposed | 3.2264 |  | Chimdemash | 103I069 | 1371 | 2021 | Summer
69 | 0 | P | S83214 | A16835 |  | Proposed | 2.5025 |  | Chimdemash | 103I069 | 1063 | 2021 | Summer
70 | 0 | P | C16569 | A16835 | 299 | Issued | 10.9626 | Not harvested | Exstew | 103I045 | 7524 | 2020 | Summer
71 | 0 | P | G38054 | A16835 | 744 | Proposed | 43.5256 |  | Wesach | 103I087 | 18487.5 | 2019 | Summer
72 | 0 | P | G36219 | A16835 | 744 | Proposed | 25.0366 |  | Clear Creek | 103I087 | 10625 | 2019 | Summer
73 | 0 | P | R77327 | A16835 |  | Proposed | 13.424 |  | Kleanza | 103I059 | 9607.8 | 2019 | Summer
74 | 0 | P | H41337 | A16835 | 715 | Retired | 46.1098 |  | Pontoon | 103I067 | 22295 | 2019 | Summer
75 | 0 | P | K51075 | A16835 |  | Proposed | 17.3511 |  | Fiddler | 103I088 | 7395 | 2022 | Summer
76 | 0 | P | K51077 | A16835 |  | Proposed | 53.454 |  | Fiddler | 103I088 | 22695 | 2022 | Summer
77 | 0 | P | K51081 | A16835 |  | Proposed | 16.324 |  | Fiddler | 103I088 | 6927.5 | 2022 | Summer
78 | 0 | P | K51703 | A16835 |  | Proposed | 59.4168 |  | Fiddler | 103I088 | 25245 | 2022 | Summer
79 | 0 | P | R77543 | A16835 |  | Proposed | 5.3716 |  | Kleanza | 103I060 | 2295 | 2021 | Summer
80 | 0 | P | H39144 | A16835 |  | Proposed | 21.2673 |  | Maroon | 103I077 | 7455 | 2019 | Summer
81 | 0 | P | T87355 | A16835 |  | Proposed | 10.1538 |  | Legate | 103I080 | 4313.75 | 2022 | Summer
82 | 0 | P | G38230 | A16835 |  | Proposed | 4.1947 |  | Wesach | 103I077 | 1785 | 2022 | Summer
83 | 0 | P | G38005 | A16835 |  | Proposed | 26.3141 |  | Wesach | 103I077 | 4890 | 2022 | Summer
84 | 0 | P | R76117 | A16835 | 428 | Issued | 24.2288 |  | Kleanza | 103I059 | 13486.5 | 2021 | Summer
85 | 0 | P | T87017 | A16835 |  | Proposed | 11.0073 |  | Legate | 103I079 | 4678 | 2021 | Summer
86 | 0 | P | T87503 | A16835 |  | Proposed | 103.4093 |  | Little Oliver | 103I079 | 19125 | 2019 | Summer
87 | 0 | P | T87509 | A16835 |  | Proposed | 27.3629 |  | Little Oliver | 103I089 | 11628 | 2019 | Summer
88 | 0 | P | T87507 | A16835 | 549 | Proposed | 4.7376 |  | Little Oliver | 103I089 | 2013 | 2019 | Summer
89 | 0 | P | C16567 | A16835 | 299 | Issued | 13.3528 | Not Harvested | Exstew | 103I045 | 5949 | 2020 | Summer
90 | 0 | P | C16568 | A16835 | 299 | Issued | 6.6943 | Not Harvested | Exstew | 103I045 | 3786 | 2020 | Summer
91 | 0 | P | T87000 | A16835 | 549 | Proposed | 4.814 |  | Legate | 103I079 | 2205 | 2021 | Summer
92 | 0 | P | P69733 | A16835 |  | Proposed | 21.6095 |  | Williams Creek | 103I039 | 9183.825 | 2018 | Summer
94 | 0 | P | C15200 | A16835 | 211 | Proposed | 7.28 |  | Exchamsiks | 103I035 | 5095.4 | 2018 | Summer
95 | 0 | P | C15202 | A16835 | 211 | Proposed | 3.5165 |  | Exchamsiks | 103I034 | 2726.5 | 2018 | Summer
96 | 0 | P | C15204 | A16835 | 211 | Proposed | 1.9333 |  | Exchamsiks | 103I034 | 1767 | 2018 | Summer
97 | 0 | P | C15203 | A16835 | 211 | Proposed | 9.7457 |  | Exchamsiks | 103I034 | 7798.8 | 2018 | Summer
98 | 0 | P | R81103 | A16835 |  | Proposed | 11.7842 |  | Kleanza | 103I060 | 14505.25 | 2022 | Summer
100 | 0 | P | KL1 | A16835 |  | Proposed | 13.6198 | Increase volume in area to support R77327 | Kleanza | 103I059 | 5780 | 2019 | Summer
101 | 0 | P | WM1 | A16835 |  | Proposed | 25.411 | Roaded. | Williams Creek | 103I049 | 10795 | 2022 | Summer
102 | 0 | P | C15023 | A16835 |  | Proposed | 101.2283 |  | Exstew | 103I045 | 42925 | 2020 | Summer
103 | 0 | P | G36023 | A16835 |  | Proposed | 65.9783 | Spruce beetle hazard | North Douglas | 103I087 | 28041 | 2022 | Summer
104 | 0 | P | HC 1 | A16835 |  | Proposed | 52.2206 |  | Hatchery Creek | 103I038 | 22100 | 2022 | Summer
105 | 0 | P | HC 2 | A16835 |  | Proposed | 19.1295 |  | Hatchery Creek | 103I038 | 8075 | 2022 | Summer
106 | 0 | P | R76050 | A16835 |  | Proposed | 61.5094 | Increase volume in area to support R76049 | Noble Five | 103I059 | 26141.5152 | 2019 | Summer
107 | 0 | P | R77541 | A16835 |  | Proposed | 15.9259 |  | Kleanza | 103I060 | 6758 | 2021 | Summer
108 | 0 | P | C15024 | A16835 |  | Proposed | 42.3927 |  | Exstew | 103I045 | 18020 | 2021 | Summer
109 | 0 | P | C15025 | A16835 |  | Proposed | 31.6859 |  | Exstew | 103I045 | 13472.5 | 2021 | Summer
110 | 0 | P | G37131 | A16835 |  | Proposed | 17.277 |  | Douglas | 103I087 | 7310 | 2022 | Summer
111 | 0 | P | C15010 | A16835 |  | Proposed | 11.9292 |  | Exstew | 103I035 | 6591 | 2021 | Summer
112 | 0 | P | P66001 | A16835 | 401 | Proposed | 14.7 |  | Williams Creek | 103I048 | 7179 | 2019 | Spring
113 | 0 | P | R77942 | A16835 |  | Proposed | 10.6 | Field marked | Kleanza | 103I060 | 4505 | 2020 | Spring
114 | 0 | P | R77944 | A16835 |  | Proposed | 45 | Field marked | Kleanza | 103I060 | 19125 | 2020 | Spring
115 | 0 | P | R77963 | A16835 |  | Proposed | 28.9 | Field marked | Kleanza | 103I060 | 12282.5 | 2020 | Spring
[9 empty] | Total volume identified: |  | 1080635.0931
[9 empty] | Annual Allocation within Kalum TSA: |  | 244037
[9 empty] | Allocation X 5 years: |  | 1220185
[9 empty] | Years of supply: |  | 4.4282
Note on J114: Rick: A&A: 13052 m3 allocation BCTS: 88228 CTR: 244037 KVL: 14454 KFP: 14454