## 2018-22
|  |  | Date of Last Update: | 2018-10-31 |  |  |  | Kitselas Forestry LP
|  |  | Updated by: | EM, RB | [6 empty] | selection logging
License | TSA/TFL | CP | "Licencee" | Block ID | Area (ha) | Vol/ha | Volume | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued) | System
A90733 | TFL(Cas) | 191 | Kitselas TFL(Cas) | 11-1 | 41.1 | 528 | 21700.8 | Cole Creek | 93L041 | All | 2019 | C | GBS
A90733 | TSA | TBA | Kitselas TSA | K16-3 | 5.7 | 425 | 2422.5 | Copper | 103I058 | All | 2019 | F | GBS
A90733 | TSA | TBA | Kitselas TSA | K17-2 | 5.3 | 425 | 2252.5 | Copper | 103I058 | All | 2020 | R | Cable
A91360 | TFL | 104 | Kitselas TFL | K18-7 | 2.1 | 544 | 1142.4 | N Copper | 103I059 | All | 2019 | F | Cable
A90733 | TSA | 109 | Kitselas TSA | K22-1 | 9.2 | 425 | 3910 | Hardscrabble | 103I079 | All | 2019 | F | Cable
A90733 | TSA | 109 | Kitselas TSA | K22-2 | 7.5 | 425 | 3187.5 | Hardscrabble | 103I079 | All | 2019 | F | Cable
A90733 | TSA | 109 | Kitselas TSA | K22-3 | 14.6 | 425 | 6205 | Hardscrabble | 103I079 | All | 2019 | F | Cable
A90733 | TSA | TBA | Kitselas TSA | K31 | 7.7 | 175 | 1347.5 | North Copper | 103I058 | All | 2021 | W | GBS
A90733 | TSA | 109 | Kitselas TSA | K45 | 17.5 | 425 | 7437.5 | Williams | 103I048 | All | 2019 | F | GBS
A91360 | TFL | TBA | Kitselas TFL | K73 | 17.1 | 425 | 7267.5 | Clore | 93L031 | All | 2021 | R | Cable
A91360 | TFL | TBA | Kitselas TFL | K74 | 19.9 | 425 | 8457.5 | Clore | 93L021 | All | 2021 | R | Cable
A91360 | TFL | TBA | Kitselas TFL | K76 | 27.8 | 425 | 11815 | Clore | 93L021 | All | 2021 | R | Cable
A91360 | TFL | 100 | Kitselas TFL | K81 | 31.7 | 550 | 17435 | East Clore | 103I050 | All | 2019 | C | GBS
A91360 | TFL | 104 | Kitselas TFL | K82 | 20.8 | 544 | 11315.2 | North Copper | 103I059 | All | 2019 | F | GBS
A91360 | TFL | 104 | Kitselas TFL | K82a | 3 | 544 | 1632 | North Copper | 103I059 | All | 2019 | F | GBS
A91360 | TFL | 104 | Kitselas TFL | K83 | 8.2 | 544 | 4460.8 | North Copper | 103I059 | All | 2019 | F | GBS
A91360 | TFL | TBA | Kitselas TFL | K84 | 32.5 | 339 | 11017.5 | Clore | 93L031 | All | 2019 | R | GBS
A91360 | TFL | TBA | Kitselas TFL | K85 | 25.9 | 425 | 11007.5 | Clore | 93L031 | All | 2021 | P | Cable
A91360 | TFL | TBA | Kitselas TFL | K88 | 57.4 | 425 | 24395 | Copper | 103I049 | All | 2020 | P | GBS
A91360 | TFL | TBA | Kitselas TSA | K65 | 7.4 | 425 | 3145 | East Clore | 103I050 | All | 2020 | P | GBS
A91360 | TFL | TBA | Kitselas TFL | K69 | 34.3 | 425 | 14577.5 | Clore | 93L021 | All | 2023 | R | Cable
A91360 | TFL | TBA | Kitselas TFL | K69a | 28.5 | 425 | 12112.5 | Clore | 93L021 | All | 2023 | R | Cable
A90733 | TSA | TBA | Kitselas TSA | K48 | 49.8 | 175 | 8715 | Lakelse | 103I047 | All | 2022 | P | GBS
A90733 | TSA | 109 | Kitselas TSA | K90 | 31.3 | 175 | 5477.5 | Hwy 37S | 103I028 | All | 2019 | F | GBS
A90733 | TSA | TBA | Kitselas TSA | K911 | 1.7 | 425 | 722.5 | Copper | 103I058 | All | 2021 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K912 | 3.8 | 425 | 1615 | Copper | 103I058 | All | 2021 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K913 | 1.2 | 425 | 510 | Copper | 103I058 | All | 2021 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K914 | 3 | 425 | 1275 | Copper | 103I058 | All | 2021 | R | GBS
A91360 | TFL | TBA | Kitselas TFL | K92 | 25.5 | 425 | 10837.5 | Copper | 103I049 | All | 2020 | P | Cable
A90733 | TSA | TBA | Kitselas TSA | K93 | 15.2 | 175 | 2660 | Williams | 103I048 | All | 2020 | W | Heli
A90733 | TSA | TBA | Kitselas TSA | K94 | 20.9 | 175 | 3657.5 | Williams | 103I048 | All | 2020 | W | Heli
A90733 | TSA | TBA | Kitselas TSA | K95 | 12.4 | 175 | 2170 | Williams | 103I048 | All | 2020 | W | Heli
A90733 | TSA | TBA | Kitselas TSA | K96a | 5.4 | 425 | 2295 | North Copper | 103I058 | All | 2021 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K96b | 13.4 | 175 | 2345 | North Copper | 103I058 | All | 2021 | R | GBS
A91360 | TFL | TBA | Kitselas TFL | K98 | 23.7 | 425 | 10072.5 | North Copper | 103I059 | All | 2021 | P | Cable
A90733 | TSA | TBA | Kitselas TSA | K99 | 15.3 | 425 | 6502.5 | Fiddler | 103I089 | All | 2020 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K100 | 9.5 | 425 | 4037.5 | Hardscrabble | 103I079 | All | 2020 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K101 | 5.2 | 425 | 2210 | North Copper | 103I058 | All | 2020 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K102 | 3.1 | 425 | 1317.5 | Shannon | 103I079 | All | 2020 | R | GBS
A90733 | TSA | TBA | Kitselas TSA | K103 | 2.8 | 425 | 1190 | Shannon | 103I079 | All | 2020 | P | GBS
[5 empty] | Total volume identified: |  | 255853.7 |  |  | Annual Cut | Years of supply
[7 empty] | 0 | A73377 | KFP NRFL
[7 empty] | 0 | A77426 | KFP FLTC
[7 empty] | 157545.4 | A91360 | Kitselas TFL | 28806 | 5.4692 | 144030
[7 empty] | 21700.8 | A90733 | Kitselas TFL(Cas) | 3500 | 6.2002 | 17500
[7 empty] | 76607.5 | A90733 | Kitselas TSA | 14554 | 5.2637 | 72770
[10 empty] | 2018 | 0
[10 empty] | 2019 | 97343.7
[10 empty] | 2020 | 64375
[10 empty] | 2021 | 58730
[10 empty] | 2022 | 8715
[10 empty] | 2023 | 26690
[10 empty] | 2024 | 0
255853.7