## 2021-25
|  |  | Date of Last Update: | 2022-03-23 |  |  |  | Kitselas Forestry LP
|  |  | Updated by: | DH, RB | [6 empty] | selection logging
License | TSA/TFL | CP | "Licencee" | Block ID | Area (ha) | Vol/ha | Volume | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
A90733 | TSA | TBA | Kitselas TSA | K100 | 9.5622 | 425 | 4063.9431 | Hardscrabb* | 103I079 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K102 | 3.0877 | 425 | 1312.2653 | Shannon | 103I079 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K16-3 | 5.7079 | 425 | 2425.8388 | Copper | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K17-2 | 5.3446 | 425 | 2271.4605 | Copper | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K31 | 7.6891 | 125 | 961.1337 | North Copp* | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K48 | 49.8747 | 125 | 6234.3326 | Lakelse | 103I047 | All | 2024 | R
A91360 | TFL | TBA | Kitselas TFL | K69 | 34.3067 | 425 | 14580.3284 | Clore | 93L021 | All | 2025 | R
A91360 | TFL | TBA | Kitselas TFL | K69a | 28.5178 | 425 | 12120.068 | Clore | 93L021 | All | 2025 | R
A91360 | TFL | TBA | Kitselas TFL | K84 | 32.5705 | 339 | 11041.3937 | Clore | 93L031 | All | 2022 | R
A91360 | TFL | TBA | Kitselas TFL | K88 | 51.2 | 425 | 21760 | Copper | 103I049 | All | 2023 | W
A90733 | TSA | TBA | Kitselas TSA | K91-1 | 1.6957 | 425 | 720.6831 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-2 | 3.7736 | 425 | 1603.7592 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-3 | 1.2276 | 425 | 521.716 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-4 | 3.0322 | 425 | 1288.6778 | Copper | 103I058 | All | 2024 | R
A91360 | TFL | TBA | Kitselas TFL | K92 | 22.5 | 425 | 9562.5 | Copper | 103I049 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K93 | 15.2541 | 125 | 1906.7589 | Williams | 103I048 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K94 | 20.9424 | 125 | 2617.8054 | Williams | 103I048 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K95 | 12.4438 | 125 | 1555.4745 | Williams | 103I048 | All | 2024 | R
A91360 | TFL | TBA | Kitselas TFL | K96 | 10.5 | 125 | 1312.5 | Copper | 103I049 | All | 2023 | P
A90733 | TSA | TBA | Kitselas TSA | K111 | 5.9 | 425 | 2507.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K112 | 11.7 | 425 | 4972.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K113 | 7.9 | 425 | 3357.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K114 | 18.5 | 425 | 7862.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K115 | 11.6 | 425 | 4930 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K116 | 5.1 | 425 | 2167.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K117 | 5 | 425 | 2125 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K118 | 7.9 | 425 | 3357.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K119 | 1.3 | 425 | 552.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K120 | 5 | 425 | 2125 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K121 | 3.7 | 425 | 1572.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K122 | 5.6 | 425 | 2380 | Kleanza | 103I059 | All | 2025 | P
A91360 | TFL | TBA | Kitselas TFL | K123 | 6.9 | 425 | 2932.5 | Copper | 103I049 | All | 2023 | R
A91360 | TFL | TBA | Kitselas TFL | K124 | 12.9 | 425 | 5482.5 | Copper | 103I049 | All | 2023 | R
A91360 | TFL | TBA | Kitselas TFL | K132 | 12.7 | 425 | 5397.5 | Copper | 103I049 | All | 2022 | F
A91360 | TFL | TBA | Kitselas TFL | K136 | 57.6 | 425 | 24480 | Copper | 103I049 | All | 2022 | R
A91360 | TFL | TBA | Kitselas TFL | K137 | 13 | 425 | 5525 | Copper | 103I049 | All | 2022 | R
A91360 | TFL | TBA | Kitselas TFL | K138 | 4.9 | 425 | 2082.5 | Copper | 103I049 | All | 2022 | W
A91360 | TFL | TBA | Kitselas TFL | K139 | 9.1 | 425 | 3867.5 | Copper | 103I059 | All | 2023 | W
A91360 | TFL | TBA | Kitselas TFL | K140 | 19.2 | 425 | 8160 | North Copper | 103I049 | All | 2023 | W
A91360 | TFL | TBA | Kitselas TFL | K142 | 6.2 | 425 | 2635 | Trapper | 103I050 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K133 | 17.4 | 425 | 7395 | Trapper | 103I050 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K144 | 8 | 425 | 3400 | North Copper | 103I049 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K145 | 8.1 | 425 | 3442.5 | Copper | 103I050 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K146 | 11.2 | 425 | 4760 | Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K147 | 7.8 | 425 | 3315 | Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K148 | 6.7 | 425 | 2847.5 | Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K98 | 30.2 | 425 | 12835 | North Copper | 103I059 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K149 | 10.1 | 425 | 4292.5 | North Copper | 103I059 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K150 | 3.7 | 425 | 1572.5 | North Copper | 103I059 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K97 | 38.9 | 425 | 16532.5 | North Copper | 103I059 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K152 | 8.9 | 425 | 3782.5 | North Copper | 103I059 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K153 | 11.6 | 425 | 4930 | Clore | 93L021 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K154 | 8.1 | 425 | 3442.5 | Clore | 93L021 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K155 | 14.9 | 425 | 6332.5 | Clore | 93L021 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K156 | 11 | 425 | 4675 | Clore | 93L021 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K158 | 22.9 | 425 | 9732.5 | Copper | 103I050 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K160 | 16.9 | 425 | 7182.5 | Clore | 103I040 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL(Cas) | K161 | 14.8 | 425 | 6290 | Kitnayakwa | 93L041 | All | 2026 | P
A91360 | TFL | TBA | Kitselas TFL | K209 | 4.1 | 425 | 1742.5 | North Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K210 | 9.7 | 425 | 4122.5 | North Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K211 | 13.8 | 425 | 5865 | North Copper | 103I049 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K212 | 5.3 | 425 | 2252.5 | North Copper | 103I050 | All | 2024 | P
A91360 | TFL | TBA | Kitselas TFL | K213 | 21.7 | 425 | 9222.5 | North Copper | 103I050 | All | 2026 | P
A91360 | TFL | TBA | Kitselas TFL | K214 | 11.4 | 425 | 4845 | North Copper | 103I050 | All | 2026 | P
A91360 | TFL | TBA | Kitselas TFL | K215 | 17.3 | 425 | 7352.5 | North Copper | 103I050 | All | 2026 | P
A91360 | TFL | TBA | Kitselas TFL | K216 | 19.5 | 425 | 8287.5 | North Copper | 103I050 | All | 2026 | P
A91360 | TFL | TBA | Kitselas TFL | K217 | 13.3 | 425 | 5652.5 | North Copper | 103I050 | All | 2026 | P
[5 empty] | Total volume identified: |  | 352435.6389 |  |  | Annual Cut | Years of supply
[7 empty] | 0 | A73377 | KFP NRFL
[7 empty] | 0 | A77426 | KFP FLTC
[6 empty] | 290000 | 280751.7901 | A91360 | Kitselas TFL | 288273 | 97.39% | FLTC is undercut by 287206 as of Dec 2020, less 75106 harvested in 2021 = volume target of 212,100 m3 prior to end of 2023 (+ Harvest of AAC in 2024 - '26)
[7 empty] | 6290 | A90733 | Kitselas TFL(Cas) | 3500 | 1.7971
[7 empty] | 65393.8488 | A90733 | Kitselas TSA | 14554 | 4.4932 | FL will be near Cut Control by early 2022, so FL vol mostly not avail 'til '24
[7 empty] | Kitselas TFL(Cas) | Kitselas TFL | Kitselas TSA |  | TOTAL
[7 empty] | 0 | 58088.8937 | 9722.3762 | 2022 | 67811.2699
[7 empty] | 0 | 132255 | 0 | 2023 | 132255 | 2023 = end Cut Control for TSA and for FLTC
[7 empty] | 0 | 28347.5 | 17761.4727 | 2024 | 46108.9727
[7 empty] | 0 | 26700.3963 | 37910 | 2025 | 64610.3963
[7 empty] | 6290 | 35360 | 0 | 2026 | 41650
[8 empty] | 280751.7901 | 65393.8488 |  | 352435.6389