## 2020-24
|  |  | Date of Last Update: | 2020-10-28 |  |  |  | Kitselas Forestry LP
|  |  | Updated by: | RB | [6 empty] | selection logging
License | TSA/TFL | CP | "Licencee" | Block ID | Area (ha) | Vol/ha | Volume | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
A90733 | TSA | TBA | Kitselas TSA | K100 | 9.5622 | 425 | 4063.9431 | Hardscrabb* | 103I079 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K102 | 3.0877 | 425 | 1312.2653 | Shannon | 103I079 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K16-3 | 5.7079 | 425 | 2425.8388 | Copper | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K17-2 | 5.3446 | 425 | 2271.4605 | Copper | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K31 | 7.6891 | 175 | 1345.5873 | North Copp* | 103I058 | All | 2022 | F
A90733 | TSA | TBA | Kitselas TSA | K48 | 49.8747 | 175 | 8728.0657 | Lakelse | 103I047 | All | 2024 | R
A91360 | TFL | 112 | Kitselas TFL | K65 | 21.7 | 425 | 9222.5 | East Clore | 103I050 | All | 2021 | F
A91360 | TFL | TBA | Kitselas TFL | K69 | 34.3067 | 425 | 14580.3284 | Clore | 93L021 | All | 2025 | R
A91360 | TFL | TBA | Kitselas TFL | K69a | 28.5178 | 425 | 12120.068 | Clore | 93L021 | All | 2025 | R
A91360 | TFL | 110 | Kitselas TFL | K76 | 23 | 425 | 9775 | Clore | 93L021 | All | 2021 | F
A91360 | TFL | 108 | Kitselas TFL | K109 | 27.4 | 425 | 11645 | Clore | 93L021 | All | 2021 | F
A91360 | TFL | 110 | Kitselas TFL | K110 | 19.3 | 425 | 8202.5 | Clore | 93L021 | All | 2021 | F
A91360 | TFL | 100 | Kitselas TFL | K81 | 31.767 | 550 | 17471.8319 | East Clore | 103I050 | All | 2022 | C
A91360 | TFL | TBA | Kitselas TFL | K84 | 32.5705 | 339 | 11041.3937 | Clore | 93L031 | All | 2022 | R
A91360 | TFL | TBA | Kitselas TFL | K88 | 57.4192 | 425 | 24403.1638 | Copper | 103I049 | All | 2023 | P
A90733 | TSA | TBA | Kitselas TSA | K91-1 | 1.6957 | 425 | 720.6831 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-2 | 3.7736 | 425 | 1603.7592 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-3 | 1.2276 | 425 | 521.716 | Copper | 103I058 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K91-4 | 3.0322 | 425 | 1288.6778 | Copper | 103I058 | All | 2024 | R
A91360 | TFL | TBA | Kitselas TFL | K92 | 25.5924 | 425 | 10876.7785 | Copper | 103I049 | All | 2022 | P
A90733 | TSA | TBA | Kitselas TSA | K93 | 15.2541 | 175 | 2669.4624 | Williams | 103I048 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K94 | 20.9424 | 175 | 3664.9275 | Williams | 103I048 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K95 | 12.4438 | 175 | 2177.6643 | Williams | 103I048 | All | 2024 | R
A90733 | TSA | TBA | Kitselas TSA | K111 | 5.9 | 425 | 2507.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K112 | 11.7 | 425 | 4972.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K113 | 7.9 | 425 | 3357.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K114 | 18.5 | 425 | 7862.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K115 | 11.6 | 425 | 4930 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K116 | 5.1 | 425 | 2167.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K117 | 5 | 425 | 2125 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K118 | 7.9 | 425 | 3357.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K119 | 1.3 | 425 | 552.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K120 | 5 | 425 | 2125 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K121 | 3.7 | 425 | 1572.5 | Kleanza | 103I059 | All | 2025 | P
A90733 | TSA | TBA | Kitselas TSA | K122 | 5.6 | 425 | 2380 | Kleanza | 103I059 | All | 2025 | P
A91360 | TFL | TBA | Kitselas TFL | K123 | 6.9 | 425 | 2932.5 | Kleanza | 103I049 | All | 2023 | P
A91360 | TFL | TBA | Kitselas TFL | K124 | 12.9 | 425 | 5482.5 | Kleanza | 103I049 | All | 2023 | P
[5 empty] | Total volume identified: |  | 208457.6152 |  |  | Annual Cut | Years of supply
[7 empty] | 0 | A73377 | KFP NRFL
[7 empty] | 0 | A77426 | KFP FLTC
[7 empty] | 137753.5643 | A91360 | Kitselas TFL | 28806 | 4.7821
[7 empty] | 0 | A90733 | Kitselas TFL(Cas) | 3500 | 0
[7 empty] | 70704.0509 | A90733 | Kitselas TSA | 14554 | 4.858