## 2018-22
Date of Last Update: | 10/31/2018 |  |  |  | Kalum Ventures Ltd
Updated by: | RB | [6 empty] | Selection logging
"Licencee" | Block ID | Area (ha) | m3/ha | Volume | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
FLTC A91358 (TFL) | 14-1 | 2.4 | 425 | 1020 | West Kalum | 103I076 | All | 2019 | W
FLA09734 (TSA) | 53-3 | 4.6 | 365 | 1679 | Amesbury | 103I047 | Winter | 2019 | C
FLA09734 (TSA) | V67 | 11.8 | 425 | 5015 | Big Cedar | 103I067 | Summer | 2021 | F
FLA09734 (TSA) | V68 | 6.9 | 425 | 2932.5 | Big Cedar | 103I067 | Summer | 2021 | F
FLA09734 (TSA) | V25-1b | 8.5 | 423 | 3510 | Big Cedar | 103I067 | Summer | 2019 | C
FLA09734 (TSA) | V25-2 | 5.8 | 372 | 1785 | Big Cedar | 103I067 | Summer | 2019 | C
FLA09734 (TSA) | V25-5b | 2.4 | 293 | 2488 | Big Cedar | 103I067 | Summer | 2019 | C
FLA09734 (TSA) | V25-5a | 0.8 | 394 | 315 | Big Cedar | 103I067 | Summer | 2019 | C
FLA09734 (TSA) | V44-5 | 0.2 | 394 | 315 | Big Cedar | 103I067 | Summer | 2019 | C
FLTC A91358 (TFL) | V71b | 2.3 | 142 | 326.6 | West Kalum | 103I067 | All | 2019 | C
FLTC A91358 (TFL) | V65 | 44.4672 | 125 | 5558.394 | West Kalum | 103I067 | All | 2019 | W
FLTC A91358 (TFL) | VNB-7 | 14.5661 | 425 | 6190.6048 | North Beaver | 103I086 | All | 2019 | F
FLTC A91358 (TFL) | VNB-4 | 1.3119 | 425 | 557.5448 | North Beaver | 103I086 | All | 2019 | F
FLA09734 (TSA) | V30 | 10.1118 | 425 | 4297.5144 | Big Cedar | 103P007 | All | 2020 | R
FLA09734 (TSA) | V31 | 5.957 | 425 | 2531.7263 | Big Cedar | 103P007 | All | 2020 | R
FLA09734 (TSA) | V45 | 13.6078 | 125 | 1700.9733 | West Kalum | 103I057 | All | 2019 | W
FLA09734 (TSA) | V47 | 12.4 | 125 | 1550 | West Kalum | 103I057 | All | 2019 | F
FLTC A91358 (TFL-Cas) | V50 | 37.7 | 425 | 16022.5 | Meadow | 103I096 | All | 2022 | F
FLTC A91358 (TFL) | V53 | 11.8348 | 543 | 6426.3165 | Poupard | 103P005 | All | 2019 | F
FLA09734 (TSA) | V56 | 2.2 | 700 | 1540 | Swansons | 103P007 | All | 2019 | C
FLTC A91358 (TFL-Cas) | V40 (c) | 11.221 | 350 | 3927.3616 | Meadow | 103I096 | All | 2021 | R
FLTC A91358 (TFL) | V40 (t) | 9.3512 | 350 | 3272.9249 | Meadow | 103I096 | All | 2021 | R
FLTC A91358 (TFL-Cas) | V112 | 1.9249 | 425 | 818.0706 | Meadow | 103P007 | All | 2021 | R
FLTC A91358 (TFL) | V4-3 | 5.372 | 125 | 671.4985 | Beaver | 103I086 | All | 2021 | R
FLTC A91358 (TFL) | V4-4 | 21.9674 | 125 | 2745.92 | Beaver | 103I086 | All | 2021 | R
FLA09734 (TSA) | V100 | 5.1159 | 425 | 2174.2362 | Glacier | 103I067 | All | 2020 | R
FLA09734 (TSA) | V110 | 10.8 | 552 | 5961.6 | Clear Creek | 103I087 | All | 2019 | F
FLTC A91358 (TFL) | V123 | 34.1176 | 125 | 4264.7043 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V124 | 17.7662 | 125 | 2220.7706 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V125 | 14.8666 | 155 | 2304.321 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V126 | 3.5434 | 125 | 442.9192 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V137 | 7.4502 | 125 | 931.2803 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V127 | 12.003 | 125 | 1500.381 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V128 | 8.3319 | 125 | 1041.4903 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V129 | 0.64894 | 425 | 275.8008 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V130 | 5.2118 | 125 | 651.4787 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V131 | 7.1065 | 125 | 888.3114 | North Beaver | 103I086 | All | 2019 | R
FLTC A91358 (TFL) | V118 | 6.3549 | 425 | 2700.8117 | Poupard | 103P005 | All | 2022 | R
FLTC A91358 (TFL) | V138 | 10.33 | 125 | 1291.2461 | West Kalum | 103I067 | All | 2020 | R
FLTC A91358 (TFL) | V59 | 13.9 | 425 | 5907.5 | West Kalum | 103I067 | All | 2021 | R
FLTC A91358 (TFL) | V139 | 17.3 | 425 | 7352.5 | West Kalum | 103I067 | All | 2021 | R
FLTC A91358 (TFL) | V140 | 6.5 | 159 | 1033.5 | West Kalum | 103I057 | All | 2022 | C
FLA09734 (TSA) | V142 | 6.5207 | 125 | 815.0847 | West Kalum | 103I057 | Winter | 2023 | F
FLA09734 (TSA) | V46 | 25.6 | 299 | 7654.4 | West Kalum | 103I057 | Winter | 2023 | F
FLA09734 (TSA) | V143 | 6.8 | 646 | 4392.8 | Swansons | 103P007 | All | 2019 | F
FLA09734 (TSA) | V144 | 3.3 | 397 | 1310.1 | Swansons | 103P007 | All | 2019 | F
FLA09734 (TSA) | V145 | 32.2 | 425 | 13685 | Swansons | 103P007 | All | 2020 | R
FLA09734 (TSA) | V146 | 5 | 425 | 2125 | Swansons | 103P007 | All | 2020 | P
FLTC A91358 (TFL) | V149 | 121.4124 | 125 | 15176.5545 | Alice Creek | 103I067 | All | 2022 | P
FLTC A91358 (TFL) | V148 | 24.761 | 125 | 3095.125 | Alice Creek | 103I067 | All | 2022 | P
FLTC A91358 (TFL) | V150 | 36.8375 | 125 | 4604.6838 | Luncheon Creek | 103I067 | All | 2020 | P
FLTC A91358 (TFL) | V151 | 39.5224 | 125 | 4940.3013 | Erlandson | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V152 | 13.8 | 425 | 5865 | Erlandson | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V153 | 9.3749 | 425 | 3984.3308 | Erlandson | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V154 | 19 | 125 | 2375 | South Beaver | 103I086 | All | 2023 | P
FLTC A91358 (TFL) | V155 | 7 | 125 | 875 | South Beaver | 103I086 | All | 2023 | P
FLTC A91358 (TFL) | V156 | 20 | 425 | 8500 | West Kalum | 103I066/067 | All | 2021 | P
FLTC A91358 (TFL) | V157 | 14 | 425 | 5950 | West Kalum | 103I066/067 | All | 2021 | P
FLTC A91358 (TFL) | V158 | 19 | 425 | 8075 | West Kalum | 103I066 | All | 2023 | P
FLTC A91358 (TFL) | V159 | 33 | 125 | 4125 | Little Cedar | 103I096 | All | 2023 | P
FLTC A91358 (TFL) | V160 | 67 | 125 | 8375 | Little Cedar | 103I096 | All | 2023 | P
FLA09734 (TSA) | V161 | 20 | 425 | 8500 | Anweiler | 103P007 | All | 2020 | P
FLA09734 (TSA) | V162 | 6 | 425 | 2550 | Anweiler | 103P007 | All | 2020 | P
| Total volume identified: |  |  | 235113.6811 | Subtotals: | 135517.8141 | FLTC A91358 (TFL) | 25391 | 5.3372
[6 empty] | 20767.9322 | FLTC A91358 (TFL-Cas) | 3500 | 5.9337
[6 empty] | 78827.9349 | FLA09734 (TSA) | 14454 | 5.4537
43345
[7 empty] | 2019 | 61148.3908
[7 empty] | 2020 | 41759.4068
[7 empty] | 2021 | 47093.2755
[7 empty] | 2022 | 38028.4912
[7 empty] | 2023 | 47084.1168
[7 empty] | 2024 | 0