## 2020-2024
Date of Last Update: | 10/31/2019 |  |  |  | Kalum Ventures Ltd
Updated by: | EM, RB | [6 empty] | Selection logging
"Licencee" | Block ID | Area (ha) | m3/ha | Volume | General Location | Mapsheet (1:20,000) | Season (Summer/Winter/All) | Projected harvest year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
FLTC A91358 (TFL) | 14-1 | 2.4033 | 425 | 1021 | West Kalum | 103I076 | All | 2024 | W
FLA09734 (TSA) | 53-1 | 14.5842 | 125 | 1823 | Amesbury | 103I047 | Winter | 2020 | C
FLA09734 (TSA) | V46 | 25.6697 | 299 | 7675 | West Kalum | 103I057 | Winter | 2020 | C
FLA09734 (TSA) | V143 | 6.8297 | 646 | 4412 | Swansons | 103P007 | All | 2020 | C
FLTC A91358 (TFL) | V4-4 | 9.4554 | 425 | 4019 | North Beaver | 103I086 | All | 2021 | F
FLTC A91358 (TFL) | V138 | 10.338 | 125 | 1292 | West Kalum | 103I067 | All | 2021 | R
FLTC A91358 (TFL) | V125 | 6.0219 | 425 | 2559 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V126 | 0.52517 | 425 | 223 | North Beaver | 103I086 | All | 2020 | R
FLTC A91358 (TFL) | V127 | 1.5314 | 425 | 651 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V128 | 0.84964 | 425 | 361 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V130 | 1.3697 | 425 | 582 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V131 | 2.4343 | 425 | 1035 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V118 | 6.3598 | 425 | 2703 | Poupard | 103P005 | All | 2022 | F
FLTC A91358 (TFL) | V59 | 41.0901 | 425 | 17463 | West Kalum | 103I067 | All | 2021 | R
FLA09734 (TSA) | V142 | 6.5258 | 125 | 816 | West Kalum | 103I057 | Winter | 2023 | F
FLA09734 (TSA) | V146 | 4.9991 | 425 | 2125 | Swansons | 103P007 | All | 2023 | P
FLTC A91358 (TFL) | V53 | 7.3856 | 543 | 4010 | Poupard | 103P005 | All | 2023 | F
FLA09734 (TSA) | V56 | 2.6835 | 700 | 1878 | Swansons | 103P007 | All | 2020 | C
FLA09734 (TSA) | V25-5b | 2.3997 | 293 | 703 | Big Cedar | 103I067 | Summer | 2021 | C
FLA09734 (TSA) | V67 | 6.9309 | 425 | 2946 | Big Cedar | 103I067 | Summer | 2021 | F
FLA09734 (TSA) | V145 | 32.2458 | 425 | 13704 | Big Cedar | 103P007 | All | 2020 | C
FLTC A91358 (TFL) | V163 | 62.3065 | 125 | 7788 | West Kalum | 103I067 | All | 2021 | P
FLTC A91358 (TFL) | V71b | 2.6467 | 142 | 376 | West Kalum | 103I067 | All | 2020 | C
FLTC A91358 (TFL) | V148 | 24.8548 | 125 | 3107 | Alice Creek | 103I067 | All | 2024 | P
FLTC A91358 (TFL) | V149 | 121.9123 | 125 | 15239 | Alice Creek | 103I067 | All | 2024 | P
FLTC A91358 (TFL) | V150 | 37.0215 | 125 | 4628 | Luncheon Cr | 103I067 | All | 2024 | P
FLTC A91358 (TFL) | V151 | 39.5612 | 125 | 4945 | Erlandson Cr | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V152 | 13.7896 | 425 | 5861 | Erlandson | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V153 | 9.4158 | 425 | 4002 | Erlandson | 103I057 | All | 2023 | P
FLTC A91358 (TFL) | V154 | 19.1003 | 125 | 2388 | South Beaver | 103I086 | All | 2023 | P
FLTC A91358 (TFL) | V155 | 7.5437 | 125 | 943 | South Beaver | 103I086 | All | 2023 | P
FLTC A91358 (TFL) | V156 | 20.5929 | 425 | 8752 | West Kalum | 103I066 | All | 2023 | P
FLTC A91358 (TFL) | V157 | 14.7487 | 425 | 6268 | West Kalum | 103I066 | All | 2023 | P
FLTC A91358 (TFL) | V158 | 11.0819 | 425 | 4710 | West Kalum | 103I066 | All | 2023 | P
FLTC A91358 (TFL) | V164 | 43.3505 | 125 | 5419 | West Kalum | 103I067 | All | 2022 | P
FLTC A91358 (TFL) | V165 | 34.3367 | 125 | 4292 | Little Cedar | 103I096 | All | 2022 | P
FLTC A91358 (TFL-Cas) | V50b | 13.8605 | 425 | 5891 | Meadow | 103I096 | All | 2022 | F
FLA09734 (TSA) | V25-1b | 8.4878 | 423 | 3590 | Big Cedar | 103I067 | Summer | 2021 | C
FLA09734 (TSA) | V25-2 | 5.8327 | 372 | 2170 | Big Cedar | 103I067 | Summer | 2021 | C
FLA09734 (TSA) | V25-5a | 0.12516 | 394 | 49 | Big Cedar | 103I067 | Summer | 2021 | C
FLA09734 (TSA) | V47 | 12.8903 | 125 | 1611 | West Kalum | 103I057 | All | 2022 | F
FLA09734 (TSA) | V30 | 20.2396 | 425 | 8602 | Big Cedar | 103P007 | All | 2024 | R
FLA09734 (TSA) | V31 | 11.9235 | 425 | 5067 | Big Cedar | 103P007 | All | 2024 | R
FLTC A91358 (TFL) | V123 | 4.4921 | 125 | 562 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V124 | 3.377 | 450 | 1520 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V40 (t) | 9.3572 | 350 | 3275 | Meadow | 103I096 | All | 2023 | R
FLTC A91358 (TFL) | V4-3 | 1.4317 | 425 | 608 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | V44-5 | 0.85362 | 394 | 336 | Big Cedar | 103I067 | Summer | 2021 | C
FLA09734 (TSA) | V45 | 27.2371 | 125 | 3405 | West Kalum | 103I057 | All | 2024 | R
FLA09734 (TSA) | V144 | 3.2578 | 397 | 1293 | Swansons | 103P007 | All | 2020 | C
FLTC A91358 (TFL) | V140 | 3.892 | 159 | 619 | West Kalum | 103I057 | All | 2022 | C
FLTC A91358 (TFL-Cas) | V50a | 25.0114 | 425 | 10630 | Meadow | 103I096 | All | 2021 | C
FLA09734 (TSA) | V110 | 1.8104 | 552 | 999 | Clear Creek | 103I087 | All | 2020 | F
FLA09734 (TSA) | V110 | 9.0139 | 552 | 4976 | Clear Creek | 103I087 | All | 2020 | F
FLTC A91358 (TFL) | V139 | 17.4501 | 425 | 7416 | West Kalum | 103I067 | All | 2022 | R
FLTC A91358 (TFL) | V65 | 44.5011 | 125 | 5563 | West Kalum | 103I067 | All | 2024 | R
FLTC A91358 (TFL) | V161 | 21.1928 | 425 | 9007 | West Kalum | 103P007 | All | 2022 | P
FLTC A91358 (TFL) | V140 | 2.7081 | 159 | 431 | West Kalum | 103I057 | All | 2022 | C
FLTC A91358 (TFL) | VNB-4 | 1.3129 | 425 | 558 | North Beaver | 103I086 | All | 2023 | F
FLTC A91358 (TFL) | VNB-7 | 3.963 | 425 | 1684 | North Beaver | 103I086 | All | 2020 | F
FLTC A91358 (TFL) | VNB-7 | 3.963 | 425 | 1684 | North Beaver | 103I086 | All | 2020 | F
| Total volume identified: |  |  | 232265 | Subtotals: | 147900 | FLTC A91358 (TFL) | 25391 | 5.8249
[6 empty] | 16521 | FLTC A91358 (TFL-Cas) | 3500 | 4.7203
[6 empty] | 67844 | FLA09734 (TSA) | 14454 | 4.6938
43345
[7 empty] | 2020 | 48605
[7 empty] | 2021 | 50986
[7 empty] | 2022 | 37389
[7 empty] | 2023 | 48653
[7 empty] | 2024 | 46632