## Sheet1
Work Progress Plan Appendix ‘H’ Contract File # 10005-40/SD24TIG204
| Nangeese | Muldoe | Deadhorse |  |  | Date | [7 empty] | Pope |  | Skilokis | Gail | Nash Y | Nichyeskwa |  | Suskwa | Helen | Comments
Deliverables | HAna023 | HAmu032 | HAde001 | HAde329 | HAde330 | HAda036 | Date 1800 Level 2 | HAdaR2 | HAdaR5 | HAdaR6 | HAdaR8 | HAda039 | DA383 | HAmu044 | HAmu046 | SK24 | T46 | HAny23 | N507 | N510 | HAga007 | A66992
Order of Multiphase work | 2 | 4 | 5 | 6 |  | 1 | [15 empty] | 3 |  | New Dev | Recce | Refurb | Road
Recce |  |  |  |  | Sept 30 2023 | [17 empty] | Planning Recce Reports, maps & spatials to be provided.
Including Report, Map & Valuations | [7 empty] | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Sept 8 2023 | Aug 18 2023 | Aug 18 2023 | Aug 18 2023 | Aug 18 2023 | Aug 18 2023 | Aug 18 2023
TSL VIA |  |  | Sept 22 2023 |  |  | July 21 2023 | [16 empty] | Submitted to BCTS Signed and Sealed
Block Terrain Assessment | [5 empty] | July 25 2023 | [16 empty] | signed and sealed
Multi phase block layout | Aug 31 2023 | Aug 31 2023 | Sept 15 2023 | Oct 6 2023 |  | July 28 2023 | [16 empty] | Field marking completed
Draft HP map and Riparian Assessments | Aug 31 2023 | Aug 31 2023 | Sept 15 2023 | Oct 6 2023 |  | July 28 2023 | [16 empty] | submit geo referenced HP map, Riparian Assessments
Block Conversion: re-layout/SP data collection | [21 empty] | Oct 6 2023 | As directed by Contract Coordinator
Block road report | Sept 29 2023 | Sept 29 2023 | Oct 16 2023 | Oct 16 2023 |  | Aug 11 2023 | [16 empty] | block road report for final road location pdf
Cruise Plan & Map (signed and sealed) | Oct 16 2023 | Oct 16 2023 | Oct 27 2023 | Oct 27 2023 |  | Aug 11 2023 | [16 empty] | Cruise plan submitted to BCTS
cruise plots field work and cards submitted | Oct 27 2023 | Nov 17 2023 | Nov 10 2023 | Nov 10 2023 |  | Aug 25 2023 | [15 empty] | Oct 6 2023 | Submitted cruise cards to BCTS for field check
Old Growth Verification on previously developed blocks - Field | [13 empty] | Aug 1 2023 | [8 empty] | Preliminary results from verification data
Old Growth Verification Report | [13 empty] | Sept 1 2023 | [8 empty] | Submitted to BCTS Signed and Sealed
Level 2 Road Location Recce, P-line and Survey | [6 empty] | Aug 4 2023 | [15 empty] | recce map and field work as described in schedule A1
Road Survey and Geometric design/drawings | [6 empty] | Aug 31 2023 | [15 empty] | Road lengths beyon first crossing by 100m
Recce |  |  |  |  | Dec 1st 2023 |  |  | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 | Dec 1st 2023 |  | As per Appendix E - Spatials and tabular updates to LRM.
LRM Entry
Dev. Summary
Site plan, SP cards, SP map and supporting documents | Nov 3 2023 | Sept 22 2023 | Oct 13 2023 | Oct 13 2023 |  | August 25 2023 | [15 empty] | Oct 20 2023 | Signed SP field card and supporting field card submitted and SP map
Harvest/Appraisal Maps (signed& sealed) & LRM data entry | Nov 3 2023 | Sept 22 2023 | Oct 13 2023 | Oct 13 2023 |  | August 25 2023 | [15 empty] | Oct 20 2023 | all items in column A for this row successful upload to LRM and final PDF files submitted
Full Cruise Compilations (including re-compilation where necessary) and Final Cruise Maps (Signed and Sealed) | Nov 30th, 2023 | Jan 15th, 2023 | Jan 30th, 2023 | Jan 30th, 2023 |  | Oct 31 2023 | [15 empty] | Dec 1 2023 | final PDF files submitted including CCP, CCO, dat & CSV files and reduction table when applicable and pdf map
Overview and locator maps | Jan 5 2024 | Jan 5 2024 | Jan 5 2024 | Jan 5 2024 |  | Jan 5 2024 | [15 empty] | Jan 5 2024 | Submitted to BCTS PDF files
Road Site Plan | [6 empty] | Aug 18 2023 | [15 empty] | Supply site plan and all relevant supporting documents include CHRE