## Full
Multi-Phase Timber Sale License Development |  |  |  |  | Work Progress Plan |  | Original
Contract: |  |  | Contractor:
TSL | BLOCK | Recce Complete | Recce Approved | Layout Complete | Layout Approved | Rework Complete | DataLoad1 Submit | DateLoad1 Loaded | Cruise Plan Submit | Check Cruise Package | Cruise Approved | DataLoad2 Submit | DateLoad2 Loaded | Initial Site Plan Submit | TSL Deliverables | Final Deliverable Round Table | Final Invoice
|  | Contractor | BCTS | Contractor | BCTS | Contractor | Contractor | BCTS | Contractor | Contractor | BCTS | Contractor | BCTS | Contractor | Contractor | BCTS | Contractor
Ministry Representative | [7 empty] | Contractor Representative
Print Name: | [7 empty] | Print Name:
Signature: | [7 empty] | Signature:
Date: | [7 empty] | Date:

## Simplified
Multi-Phase Timber Sale License Development |  |  |  |  | Work Progress Plan |  | Original
Contract: |  |  | Contractor:
TSL | Block | Recce Submission | Block & Road Layout Submission | DataLoad1 Submission1 | Check Cruise Pkge Submission2 | DataLoad2 Submission1 | Deliverables Submission3
Phase: |  | I | II | II | III | II, III, IV | II, III, IV
1Consistent with the Appendix 4 Digital Submission Standards.
2Check Cruising may not be possible if snow depths prevent ability to complete full check.
3Avoid Deliverables Submissions dates in March (fiscal year end) if possible.
Contractor Representative or Project Supervisor
Name:
Signature:
Date:
Ministry Representative
Name:
Signature:
Date:

## Property
Property supplied by the Province:
(as per Sched A, clause 4.05)
Provided | Description
Y | BMP - Temporary Winter Stream Crossings document
Y | Appendix 4 of the Field Verification of Priority Old Growth Deferral Areas document
Y | Fisher Habitat Management Tables for Sub Boreal Spruce document
Y | NIPC's Guide to Invasive Plants document
Y | TSN's Guide for Moose Management document
Y | BCFSC's Steep Slope Logging document